## All Features + Budget
HumanPages: COMPLETE Feature List — All Sessions, All Ideas, All Budgets
40 features from 6 architect agents + 15 feature specs + war rooms + action plans. Claude cost = $0 for all code. External costs shown.
# | Feature | Category | Day | Claude Hrs | Claude $ | External $ | External Detail | Total $ | Source | Personas Served
1 | Progressive Trust Tiers | Trust | D1 | 3 | $0 | $0 | — | $0 | Architects + features/graduated-trust.md | ALL
2 | Sybil-Resistant Reputation Algorithm | Trust | D1 | 2 | $0 | $0 | — | $0 | Trust architect | ALL
3 | Atomic Task Decomposition (Milestones) | Trust | D2 | 2 | $0 | $0 | — | $0 | Trust architect | ALL
4 | Streaming Quality Gates (Superfluid) | Trust | D2 | 2 | $0 | $0 | — | $0 | Trust architect + existing code | ALL
5 | Self-Staked Reputation Bonds | Trust | D3 | 4 | $0 | $50-150 | Smart contract peer audit | $50-150 | DAO/DeFi architects | DAO, DeFi, Web3
6 | Community Arbitration + Dispute System | Trust | D3 | 3 | $0 | $0 | — | $0 | Trust architect + features/escrow-moltcourt.md | ALL
7 | Batch MCP Tools (7 new) | MCP | D3 | 4 | $0 | $0 | — | $0 | AI Agent CTO architect | AI Agents
8 | Mutual Ratings (Human rates Agent) | Platform | D4 | 3 | $0 | $0 | — | $0 | features/mutual-ratings.md | ALL
9 | Agent Identity + Reputation | Platform | D4 | 3 | $0 | $0 | — | $0 | features/agent-identity.md | ALL
10 | Task Bounties (Public Job Board) | Platform | D4 | 4 | $0 | $0 | — | $0 | features/task-bounties.md | ALL
11 | Bulk Hiring Campaigns | Platform | D5 | 3 | $0 | $0 | — | $0 | DAO architect | DAO, Web3
12 | Response Time + Activity Tracking | Platform | D5 | 2 | $0 | $0 | — | $0 | features/response-tracking.md | ALL
13 | Human Verification (Social OAuth + Humanity Protocol) | Verification | D5 | 3 | $0 | $0 | Gitcoin Passport = free API | $0 | features/human-verification.md | ALL
14 | Domain Expert Verification (Portfolio) | Verification | D6 | 3 | $0 | $100-200 | Seed 20-50 expert profiles via outreach | $100-200 | DeFi architect | DeFi, DAO
15 | CryptoCredential Search | Search | D6 | 3 | $0 | $0 | — | $0 | DeFi architect | DeFi
16 | Fuzzy Search + Denormalized Index | Search | D6 | 3 | $0 | $0 | — | $0 | Architecture docs | ALL
17 | Availability Calendar + Scheduling | Platform | D7 | 3 | $0 | $0 | — | $0 | API specs + architecture | ALL
18 | AI-Generated Job Descriptions | Platform | D7 | 2 | $0 | $0 | Claude API already integrated | $0 | Architecture docs | ALL
19 | RLHF Qualification System | RLHF | D7 | 4 | $0 | $300-500 | RLHF expert writes 48 gold-standard Qs | $300-500 | RLHF architect | RLHF
20 | QA Pipeline (5-phase) | RLHF | D8 | 5 | $0 | $100-200 | Test with 20 real annotators | $100-200 | RLHF architect | RLHF
21 | Regional Talent Networks | Supply | D8 | 2 | $0 | $50-100 | Freelancer posts in 10 regional groups | $50-100 | Web3 architect | Web3, RLHF
22 | Proof-of-Work Portfolio (IPFS + on-chain) | Trust | D8 | 2 | $0 | $0 | — | $0 | Web3 architect + architecture docs | Web3, DAO
23 | Swarm Mode (MTurk-style micro-tasks) | Platform | D8 | 5 | $0 | $0 | — | $0 | features/swarm-mode.md | AI Agents, RLHF
24 | Retainer/Streaming Teams | Platform | D9 | 3 | $0 | $0 | — | $0 | Web3 architect + architecture docs | Web3, DAO
25 | Cohort Recruitment Engine | Supply | D9 | 3 | $0 | $0 | — | $0 | RLHF architect | RLHF
26 | Transparency + Audit Trail (EAS attestations) | Trust | D9 | 2 | $0 | $0 | — | $0 | features/transparency-audit.md | ALL
27 | Cross-Protocol Reputation Import/Export | Trust | D9 | 3 | $0 | $0 | — | $0 | Architecture docs | DeFi, DAO
28 | Wallet On-Ramp (Coinbase Pay) + Off-Ramp (Wise) | Payments | D9 | 3 | $0 | $0 | Both have free APIs | $0 | Architecture docs | ALL
29 | Tax Automation (1099/W-8) | Compliance | D10 | 3 | $0 | $100-200 | Quick legal review of tax forms | $100-200 | RLHF architect | RLHF, Web3
30 | Autonomous Agent Verification (AgentKit) | MCP | D10 | 2 | $0 | $0 | AgentKit already integrated | $0 | Architecture docs | AI Agents
31 | Webhooks + Async Pipeline | MCP | D10 | 2 | $0 | $0 | — | $0 | Architecture docs + MCP specs | AI Agents
32 | ERC-8004 Oracle Bridge (weekly batch publish) | Trust | D10 | 2 | $0 | $0 | Base L2 gas: ~$0.50/batch | $0 | features/erc8004-compatibility.md | ALL
33 | Integration Testing + Polish | QA | D10 | 6 | $0 | $50-100 | Pay 5-10 beta testers | $50-100 | — | ALL
34 | Reddit Outreach (10 subreddits daily) | Supply | D1-10 | 0 | $0 | $0-50 | You or $3-5/post freelancer | $0-50 | War room + action plan | ALL
35 | BTCMap Business Outreach (25K contacts) | Supply | D1-10 | 0 | $0 | $100-300 | Cheap freelancers $3-5/hr | $100-300 | Enrichment skill + action plan | ALL
36 | Telegram/Discord Group Posts (20-30 groups) | Supply | D2-5 | 0 | $0 | $0-30 | Freelancer or you | $0-30 | TG bot warroom | ALL
37 | Twitter/Farcaster/Lens Crypto Threads | Supply | D1-5 | 0 | $0 | $0 | You (authentic founder voice) | $0 | Action plan | DeFi, DAO, Web3
38 | MTurk Supply Campaign (50 US states + India) | Supply | D3-10 | 0 | $0 | $350-750 | $0.50-0.75/signup × 700-1000 | $350-750 | Session export + enrichment | ALL
39 | SproutGigs High-Wage Country Campaign | Supply | D3-10 | 0 | $0 | $280-500 | $0.35-0.50/signup × 800-1000 | $280-500 | Session export | ALL
40 | Expert Recruiting (DeFi specialists) | Supply | D4-10 | 0 | $0 | $50-100 | DM 50 Solidity auditors on Twitter | $50-100 | War room | DeFi
41 | RLHF Annotator Recruitment | Supply | D5-10 | 0 | $0 | $50-100 | Post in Prolific/Toloka alumni communities | $50-100 | RLHF architect | RLHF
42 | Referral Program ($5 USDC per activated human) | Supply | D4+ | 2 | $0 | $250-500 | $5 × 50-100 referred humans | $250-500 | War room | ALL
43 | Demo Videos (3 killer demos) | Marketing | D1-2 | 0 | $0 | $15-40 | Screen recording + editing | $15-40 | Action plan | ALL
44 | FB Group Campaign (10-15 groups/day) | Marketing | D3-10 | 0 | $0 | $0-100 | Marketer at $3-5/hr or you | $0-100 | Creative ideas / ad copy | ALL
45 | Video Testimonials (100 videos @ $3 each) | Marketing | D7+ | 0 | $0 | $300 | 100 users × $3/video | $300 | Session export | ALL
46 | Social Posts (300 posts @ $1 each) | Marketing | D7+ | 0 | $0 | $300 | 300 users × $1/post | $300 | Session export | ALL
47 | GEO: Third-Party Articles + Listings | Marketing | D5-10 | 0 | $0 | $0-100 | Commission 3-5 comparison articles | $0-100 | Detailed API specs / GEO strategy | ALL
48 | Content Marketing (3 blog posts, Claude writes) | Marketing | D5-10 | 2 | $0 | $0 | Claude writes, you publish on Dev.to/Hashnode | $0 | Action plan | ALL
49 | Website Messaging Rewrite (homepage + /dev) | Website | D1-2 | 3 | $0 | $0 | — | $0 | War room website optimization | ALL
50 | Fix Pricing Bugs ($10/day → $10/month) | Website | D1 | 0.5 | $0 | $0 | — | $0 | War room | ALL
51 | OG Tags + Social Previews | Website | D1 | 1 | $0 | $0 | Already partially built in seo.ts | $0 | CLAUDE.md | ALL
52 | Rotating Headlines (A/B tested) | Website | D2 | 1 | $0 | $0 | — | $0 | rotating-headlines-ranked.md | ALL
53 | ListingLink Short Codes (/work/:code) | Website | D2 | 2 | $0 | $0 | — | $0 | Dev connect plan | ALL
54 | Internationalization (8 languages Phase 1) | Website | D9-10 | 4 | $0 | $100-200 | Translators for 7 languages | $100-200 | features/internationalization.md | ALL
| GRAND TOTAL (54 items) |  | 10 days | ~100 hrs | $0 | $2,195-4,320 |  | $2,195-4,320 | All sessions | ALL

## Budget Summary
Budget Summary by Category
Category | # Features | Claude Hours | Claude Cost | External Low | External High | What External $ Buys
Trust (6 features) | 6 | ~16 hrs | $0 | $50 | $150 | Smart contract peer audit only
Platform (9 features) | 9 | ~28 hrs | $0 | $0 | $0 | All pure Claude code
MCP/Agent (4 features) | 4 | ~11 hrs | $0 | $0 | $0 | All pure Claude code — extends existing infra
Verification (2 features) | 2 | ~6 hrs | $0 | $100 | $200 | Seeding expert profiles via outreach
Search (2 features) | 2 | ~6 hrs | $0 | $0 | $0 | All pure Claude code
RLHF (3 features) | 3 | ~12 hrs | $0 | $400 | $700 | Gold-standard questions ($300-500) + test annotators ($100-200)
Payments/Compliance (2 features) | 2 | ~6 hrs | $0 | $100 | $200 | Legal review of tax forms
Website/UX (6 features) | 6 | ~11.5 hrs | $0 | $100 | $200 | Translations for i18n
QA/Testing (1 feature) | 1 | ~6 hrs | $0 | $50 | $100 | Beta testers
SUBTOTAL: CODE | 33 | ~100 hrs | $0 | $800 | $1,550 | Features only
Supply Acquisition (10 tracks) | 10 | 2 hrs | $0 | $1,095 | $2,470 | MTurk + SproutGigs + outreach + referrals
Marketing (5 tracks) | 5 | 2 hrs | $0 | $315 | $540 | Videos + posts + articles + FB groups
GRAND TOTAL | 54 | ~104 hrs | $0 | $2,195 | $4,320 | 33 features + 15 parallel growth tracks

## 10-Day Sprint (Full)
10-Day Sprint: ALL 54 Items (33 Features + 15 Supply/Marketing + 6 Website)
~3-4 Claude sessions/day. Each session ships a tested feature. Supply + marketing run in parallel.
Day | Session | Code Features | Parallel: Supply/Marketing | Website Fixes | Features Done | Cumulative $ | Score | Notes
DAY 1 | AM+PM+EVE | 1. Progressive Trust Tiers 2. Sybil-Resistant Reputation 3. Batch MCP Tools (7 new) | Reddit outreach starts (daily from now) Twitter/X crypto thread posted Demo videos recorded (3 clips) | Fix pricing bugs OG tags + social previews Start homepage rewrite | 3 of 33 | $15-40 | 4.5 | Trust foundation + MCP in 1 day. Supply outreach starts immediately.
DAY 2 | AM+PM+EVE | 4. Atomic Task Decomposition 5. Streaming Quality Gates 6. Community Arbitration | BTCMap business outreach starts Telegram/Discord group posts begin Farcaster/Lens posts | Rotating headlines ListingLink short codes | 6 of 33 | $100-330 | 5.8 | All 6 trust mechanisms done in 2 days. Zero-escrow system complete.
DAY 3 | AM+PM+EVE | 7. Self-Staked Bonds (+ contract) 8. Mutual Ratings 9. Agent Identity + Reputation | MTurk campaign launches (50 states + India) SproutGigs campaign launches Expert recruiting begins | Website rewrite continues | 9 of 33 | $830-1,730 | 6.5 | Stakes need $50-150 audit. MTurk/SproutGigs are biggest spend.
DAY 4 | AM+PM+EVE | 10. Task Bounties 11. Response Tracking 12. Human Verification (OAuth + Humanity) | Referral program goes live ($5/activated) FB group campaign starts (10-15 groups/day) DAO partnership DMs | — | 12 of 33 | $830-1,830 | 7.0 | Public job board live. Agents can browse humans. Humans can browse jobs.
DAY 5 | AM+PM+EVE | 13. Bulk Hiring Campaigns 14. Domain Expert Verification 15. CryptoCredential Search | RLHF annotator recruitment starts GEO: comparison articles commissioned Content marketing (Claude writes 3 posts) | — | 15 of 33 | $1,030-2,230 | 7.8 | DAO Ops fully unblocked. DeFi mostly unblocked.
DAY 6 | AM+PM+EVE | 16. Fuzzy Search + Denormalized Index 17. Availability Calendar 18. AI-Generated Job Descriptions | Continue all active supply campaigns Publish first blog posts on Dev.to/Hashnode | — | 18 of 33 | $1,030-2,230 | 8.0 | Search quality massively improved. Calendar enables scheduling.
DAY 7 | AM+PM+EVE | 19. RLHF Qualification System 20. Proof-of-Work Portfolio 21. Regional Talent Networks | Video testimonial campaign starts (100 × $3) Social post campaign starts (300 × $1) Continue supply campaigns | — | 21 of 33 | $1,680-3,430 | 8.5 | RLHF gold-standard Qs are $300-500 external. Biggest expert cost.
DAY 8 | AM+PM+EVE | 22. QA Pipeline (5-phase) 23. Swarm Mode 24. Cohort Recruitment Engine | Continue all campaigns First MTurk/SproutGigs results coming in (~500-1000 signups) | — | 24 of 33 | $1,780-3,630 | 8.8 | Swarm Mode = MTurk competitor. RLHF Company fully unblocked.
DAY 9 | AM+PM+EVE | 25. Retainer/Streaming Teams 26. Transparency + Audit Trail 27. Cross-Protocol Reputation 28. Wallet On/Off-Ramp | Continue all campaigns First referral signups arriving DAO partnership responses | Internationalization (8 languages) | 28 of 33 | $1,980-4,030 | 9.0 | All personas at 9.0. Retainers enable ongoing team relationships.
DAY 10 | AM+PM+EVE | 29. Tax Automation 30. Agent Verification (AgentKit) 31. Webhooks + Async 32. ERC-8004 Oracle Bridge 33. Integration Testing | MTurk/SproutGigs final results (~1500-2000 total signups) First 50+ video testimonials in First 150+ social posts in | Polish i18n + final fixes | 33 of 33 | $2,195-4,320 | 9.2 | All 33 features shipped. All supply campaigns running. DONE.

## Supply + Marketing Budget
Supply Acquisition + Marketing: Detailed Budget
Track | Channel | Who Executes | Days Active | Cost Low | Cost High | Expected Signups | Cost/Signup | Priority
SUPPLY | Reddit (10 subreddits daily) | You or $3-5/post freelancer | D1-10 | $0 | $50 | 200-500 | $0-0.25 | P0
SUPPLY | BTCMap Outreach (25K businesses) | Cheap freelancers $3-5/hr | D1-10 | $100 | $300 | 500-2000 aware, 50-200 list | $0.50-1.50 | P0
SUPPLY | MTurk Campaign (50 US states + India) | Automated (HIT per state) | D3-10 | $350 | $750 | 700-1000 | $0.50-0.75 | P1
SUPPLY | SproutGigs (17 high-wage countries) | Automated campaigns | D3-10 | $280 | $500 | 800-1000 | $0.35-0.50 | P1
SUPPLY | Telegram/Discord Groups (20-30) | Freelancer or you | D2-5 | $0 | $30 | 100-300 | $0-0.10 | P1
SUPPLY | Twitter/Farcaster/Lens | You (founder voice) | D1-5 | $0 | $0 | 50-200 | FREE | P1
SUPPLY | Expert Recruiting (DeFi) | DM 50 specialists on Twitter | D4-10 | $50 | $100 | 5-15 | $7-20/expert | P2
SUPPLY | RLHF Annotator Recruitment | Post in Prolific/Toloka alumni | D5-10 | $50 | $100 | 200-500 | $0.20-0.50 | P2
SUPPLY | Referral Program ($5 USDC) | Automated on-platform | D4+ | $250 | $500 | 50-100 | $5.00 | P2
SUPPLY | DAO Partnership DMs | You | D4-10 | $0 | $0 | 2-5 DAOs (× 50-200 humans) | FREE | P2
SUPPLY SUBTOTAL |  |  | 10 days | $1,080 | $2,330 | 2,657-5,815 signups | $0.40-0.88 avg
MARKETING | Demo Videos (3 clips) | You (screen record) | D1-2 | $15 | $40 | Trust-builder | N/A | P0
MARKETING | FB Group Campaign (10-15 groups/day) | Marketer at $3-5/hr or you | D3-10 | $0 | $100 | 50-200 | $0-0.50 | P1
MARKETING | Video Testimonials (100 videos) | Hire via HumanPages ($3/video) | D7+ | $300 | $300 | Social proof | $3/video | P2
MARKETING | Social Posts (300 posts) | Hire via HumanPages ($1/post) | D7+ | $300 | $300 | Social proof | $1/post | P2
MARKETING | GEO Articles + Listings | Commission or write | D5-10 | $0 | $100 | LLM visibility | Long-term | P2
MARKETING | Content: 3 blog posts (Claude writes) | Claude + you publish | D5-10 | $0 | $0 | 20-50/month ongoing | FREE | P3
MARKETING SUBTOTAL |  |  | 10 days | $615 | $840 | Brand + social proof
FEATURE EXTERNAL COSTS |  |  |  | $800 | $1,550 | Contract audit + RLHF expert + testing
GRAND TOTAL |  |  | 10 days | $2,495 | $4,720 | 2,657-5,815 signups + 33 features

## Expected Outcomes
Expected Outcomes After 10-Day Sprint
Metric | Before Sprint | After Sprint (Conservative) | After Sprint (Optimistic) | What Drives It
Platform Features | ~20 (basic) | 53 (33 new features) | 53 | Claude builds all code
MCP Tools | 16 | 23+ (7 new batch tools) | 29+ (full expansion) | Existing pattern, fast to add
Trust Mechanisms | 0 (no escrow, no protection) | 6 interlocking mechanisms | 6 + on-chain oracle | Trust system ships Day 1-3
Human Signups | 1,500 | 4,000-5,000 | 7,000-8,000 | MTurk + SproutGigs + organic
Countries Represented | 51 | 60-70 | 80+ | SproutGigs targets 17 new high-wage countries
US State Coverage | Partial | All 50 states | All 50 states | MTurk HIT per state
Crypto Specialists | ~5-10 | 15-25 | 30-50 | Expert recruiting on Twitter/Farcaster
RLHF Annotators | ~0 qualified | 200-500 | 500-1000 | Prolific/Toloka alumni + qualification test
Avg Score (5 Crypto Personas) | 3.2/10 | 8.5-9.0/10 | 9.0-9.5/10 | 33 features across all complaints
Video Testimonials | 0 | 50-75 | 100+ | $3/video via platform
Social Posts | 0 | 150-200 | 300+ | $1/post via platform
Blog Posts (Dev.to/Hashnode) | 0 | 3 | 5+ | Claude writes, you publish
Active Job Listings | ~20 | 50-100 | 200+ | Task Bounties + Swarm Mode unlock volume
Total Budget Spent | $0 | $2,195 | $4,320 | See Budget Summary sheet
Cost per New Human Signup | N/A | $0.40-0.88 | $0.35-0.60 | Blended across all channels
Days to Build | N/A | 10 | 10 | 100x development speed