## 100x Dashboard
HumanPages: 3.2 → 9+ in 10 DAYS, Not 12 Weeks
Claude builds a feature per SESSION, not per week. 18 features ÷ ~2 features/day = 9 working days.
WHY 10 DAYS, NOT 12 WEEKS
Traditional Dev (12 weeks) | Claude 100x (10 days) | Why Faster | Risk
1 dev writes Progressive Tiers in 5 days | Claude writes + tests in 3-4 hours | No context switching. Full codebase in memory. Writes tests simultaneously. | LOW — straightforward DB + API logic
1 dev builds Streaming Payment gates in 5 days | Claude extends existing Superfluid in 2-3 hours | Superfluid already integrated. Just adding pause/quality-gate triggers. | LOW — building on existing code
1 dev builds Atomic Decomposition in 5 days | Claude adds milestones[] to Job model in 2 hours | Simple schema change + payment trigger logic. Well-defined spec. | LOW — data model extension
1 dev writes 7 MCP tools in 2 weeks | Claude writes 7 MCP tools in 1 day | mcp-tools.ts pattern already exists. Each tool is copy-paste-modify. | LOW — existing pattern to follow
1 dev builds Reputation Staking in 2 weeks | Claude writes Stake model + API + contract in 4-5 hours | Prisma model + 3 API routes + minimal Solidity. Claude does all three. | MEDIUM — smart contract needs audit
1 dev builds RLHF Qualification in 3 weeks | Claude builds qualification model + test engine in 1 day | Database model + API + 48-question test. Complex but well-specified. | MEDIUM — needs real annotator testing
PERSONA SCORE TARGETS
Persona | Current | After Day 3 | After Day 6 | After Day 10 | Key Unlock | Confidence | Bottleneck
DAO Ops ($2-10M) | 3.5 | 5.5 | 8.0 | 9.5 | Trust Tiers + Bulk Campaigns | HIGH | None — all features are backend
DeFi Protocol ($50M+) | 2.0 | 4.0 | 7.0 | 9.0 | CryptoCredential + Staking | MEDIUM | Expert supply (need 50+ crypto specialists)
AI Agent CTO (100+ agents) | 4.0 | 7.0 | 9.0 | 9.5 | Batch MCP Tools (Day 2-3) | HIGHEST | None — extends existing MCP infra
Web3 Founder ($5M) | 3.5 | 5.5 | 8.0 | 9.0 | Regional Networks + Proof-of-Work | MEDIUM | Geographic supply growth
RLHF Company (50K tasks) | 4.0 | 5.0 | 7.0 | 9.0 | Qualification + QA Pipeline | LOW-MED | Need 10K annotators (supply)
BOTTOM LINE: 18 features. 10 working days. Average projected score: 9.2/10. Main risk is SUPPLY, not CODE.

## Budget Breakdown
Budget Breakdown: 10-Day Sprint to 9+/10
Claude sessions = $0 marginal cost (included in subscription). Budget is for non-code work running in parallel.
PER-FEATURE COST (Claude Dev + External)
Day | Feature | Claude Cost | External Cost | External Detail | Total | Cumulative | Notes
D1 AM | Progressive Trust Tiers | $0 | $0 | — | $0 | $0 | Pure Claude code. ~3hrs.
D1 PM | Sybil-Resistant Reputation | $0 | $0 | — | $0 | $0 | Pure Claude code. ~2hrs.
D2 AM | Atomic Task Decomposition | $0 | $0 | — | $0 | $0 | Pure Claude code. ~2hrs.
D2 PM | Streaming Quality Gates | $0 | $0 | — | $0 | $0 | Extends existing Superfluid. ~2hrs.
D3 AM | Batch MCP Tools (7 new) | $0 | $0 | — | $0 | $0 | Follows existing mcp-tools.ts pattern. ~4hrs.
D3 PM | Self-Staked Reputation Bonds | $0 | $50-150 | Smart contract audit (quick review on Code4rena or peer review) | $50-150 | $50-150 | Contract is minimal (~100 lines). Peer audit sufficient.
D4 AM | Community Arbitration | $0 | $0 | — | $0 | $50-150 | Pure Claude code. ~3hrs.
D4 PM | Bulk Hiring Campaigns | $0 | $0 | — | $0 | $50-150 | Pure Claude code. ~3hrs.
D5 AM | Domain Expert Verification | $0 | $100-200 | Seed 20-50 expert profiles via Reddit outreach + freelancer sourcing | $100-200 | $150-350 | Need real experts to test verification flow.
D5 PM | CryptoCredential Search | $0 | $0 | — | $0 | $150-350 | Pure Claude code. ~3hrs.
D6 AM | Regional Talent Networks | $0 | $50-100 | Freelancer to post in 10 regional Telegram/Discord groups | $50-100 | $200-450 | Outreach to SE Asia, LATAM, Africa communities.
D6 PM | Proof-of-Work Portfolio | $0 | $0 | — | $0 | $200-450 | Pure Claude code. ~2hrs.
D7 AM | RLHF Qualification System | $0 | $300-500 | RLHF expert writes 48 gold-standard questions + calibration set | $300-500 | $500-950 | Critical: need domain expert for test quality.
D7 PM | QA Pipeline (Phase 1-3) | $0 | $0 | — | $0 | $500-950 | Pure Claude code. ~3hrs.
D8 AM | QA Pipeline (4-5) + Cohort Recruit | $0 | $100-200 | Test with 20 real annotators ($5-10 each for test batch) | $100-200 | $600-1,150 | Need real humans to validate QA pipeline works.
D8 PM | Retainer/Streaming Teams | $0 | $0 | — | $0 | $600-1,150 | Pure Claude code. ~3hrs.
D9 AM | Tax Automation (1099/W-8) | $0 | $100-200 | Legal review of tax form compliance (quick consult) | $100-200 | $700-1,350 | Tax forms need basic legal sign-off.
D9 PM | Cross-Protocol Reputation | $0 | $0 | — | $0 | $700-1,350 | Pure Claude code. ~3hrs.
D10 | Integration Testing + Polish | $0 | $50-100 | Pay 5-10 beta testers to run through full flow | $50-100 | $750-1,450 | Real-user testing catches edge cases.
| TOTAL (18 FEATURES) | $0 | $750-1,450 |  | $750-1,450 | $750-1,450 | 18 features built + tested
PARALLEL TRACK: Supply Growth Budget (Runs Alongside Claude Dev)
Track | What | Who Does It | Duration | Cost | Expected Result | ROI | Priority
Reddit Outreach | Daily posts in r/forhire, r/cryptocurrency, r/freelance, r/remotework + 6 more | You (Itai) or $3-5/post freelancer | 10 days (daily) | $0-50 | 200-500 new signups | 10-25 signups per $1 | P0 — START DAY 1
BTCMap Business Outreach | Contact 25K crypto-accepting businesses from existing DB | Cheap freelancers ($3-5/hr) via HumanPages itself | 10 days parallel | $100-300 | 500-2,000 businesses aware, 50-200 list humans | 1-2 humans per $1 | P0 — START DAY 1
Crypto Telegram Groups | Post in 20-30 crypto freelancer Telegram groups | Freelancer or you | 3 days | $0-30 | 100-300 signups | Near-free | P1 — DAY 2
Twitter/X Crypto Thread | 5-tweet thread: "We built Fiverr for crypto. 0% fees. USDC direct." | You (authentic founder voice) | 1 day | $0 | 50-200 signups if it lands | Free | P1 — DAY 1
Farcaster/Lens Posts | Post in crypto-native social. Target DAO operators, DeFi teams. | You | 2 days | $0 | 20-50 high-quality leads | Free, high quality | P1 — DAY 3
Expert Recruiting (DeFi) | DM 50 Solidity auditors, regulatory researchers on Twitter/LinkedIn | You or freelancer | 5 days | $50-100 | 5-15 expert signups | $7-20 per expert | P2 — DAY 4
RLHF Annotator Recruitment | Post in annotation communities (Prolific, Toloka alumni, r/beermoney) | Freelancer | 5 days | $50-100 | 200-500 annotator signups | 2-5 annotators per $1 | P2 — DAY 5
DAO Partnership Outreach | DM 20 DAO ops leads offering free trial (first 10 hires free) | You | 5 days | $0 | 2-5 DAO partnerships | Free but high-effort | P2 — DAY 5
Referral Incentive Program | $5 USDC per referred human who completes first job | Automated (Claude builds referral system Day 4) | Ongoing | $250-500 | 50-100 referred humans | $5 per activated human | P2 — DAY 4
Content Marketing | 3 blog posts: "Why crypto freelancers earn more", "DAO hiring guide", "AI agent hiring" | Claude writes, you publish on Dev.to/Hashnode | 3 days | $0 | SEO long-tail, 20-50 signups/month ongoing | Free, compounds | P3 — DAY 7
| TOTAL SUPPLY GROWTH |  | 10 days parallel | $450-1,080 | 1,000-3,500 new signups | ~$0.30-1.00 per signup
GRAND TOTAL: 10-DAY SPRINT
Category | Claude Cost | External Cost | Total Budget | Deliverable
Code (18 features) | $0 (Claude) | $750-1,450 (external) | $750-1,450 | All 18 features built, tested, deployed
Supply Growth (parallel) | $0 (Claude content) | $450-1,080 (outreach) | $450-1,080 | 1,000-3,500 new human signups
GRAND TOTAL | $0 | $1,200-2,530 | $1,200-2,530 | 18 features + 1K-3.5K new humans in 10 days
Compare: Fiverr spent $30M+ to reach this feature set. Budget here: ~$1,200-2,500 + 10 days of your time.

## 10-Day Sprint
10-Day Claude Sprint: Feature-per-Session Execution Plan
Each "session" = 1 Claude Cowork session. ~2 sessions/day. Each session ships a complete, tested feature.
Day | Session | Feature | What Claude Builds | Files Touched | Tests | Personas Unblocked | Score After | Budget
DAY 1 | AM | Progressive Trust Tiers | Add trustTier enum + field to Human model. Job creation validates tier vs amount. Auto-promote endpoint. Migration. | schema.prisma, humans.ts, jobs.ts, types.ts | 8 unit tests | ALL (foundation) | 3.2 → 4.2 | $0
| PM | Sybil-Resistant Reputation Algorithm | New reputation scoring: 40% value_completed + 25% consistency + 20% age + 15% stake. Cron job to recalculate. | reputation.ts (new), humans.ts, schema.prisma | 6 unit tests | ALL (trust signals) | 4.2 → 4.8 | $0
DAY 2 | AM | Atomic Task Decomposition | Add milestones[] to Job model. Payment triggers per milestone. Auto-split endpoint for large jobs. | schema.prisma, jobs.ts, types.ts, mcp-tools.ts | 7 unit tests | ALL ($500+ jobs) | 4.8 → 5.3 | $0
| PM | Streaming Payment Quality Gates | Extend Superfluid: auto-pause on missed checkpoint, quality-gate triggers, stream-resume on approval. | superfluid.ts, jobs.ts, webhooks.ts | 5 unit tests | ALL (ongoing work) | 5.3 → 5.8 | $0
DAY 3 | AM | Batch MCP Tools (7 new) | batch_create_jobs, qualify_humans, stream_payment, monitor_batch, auto_review, template_clone, webhook_pipeline. | mcp-tools.ts, jobs.ts, humans.ts | 14 unit tests (2/tool) | AI Agent CTO → 7.0 | 5.8 → 6.5 | $0
| PM | Self-Staked Reputation Bonds | Stake model in Prisma. Wallet signature verification. Lock/unlock API. Tier display on profiles. | schema.prisma, stake.ts (new), humans.ts, profile page | 8 unit tests | DAO + DeFi partially | 6.5 → 7.0 | $50-150
DAY 4 | AM | Community Arbitration | Dispute model. Random arbitrator selection (Tier 3+). 72hr voting. Reputation impact on resolution. | schema.prisma, disputes.ts (new), reputation.ts | 9 unit tests | ALL (dispute handling) | 7.0 → 7.3 | $0
| PM | Bulk Hiring Campaigns | Campaign model with slots. Auto-match by skill+location. Dashboard API. Backfill triggers. | schema.prisma, campaigns.ts (new), humans.ts, jobs.ts | 8 unit tests | DAO Ops → 8.0 | 7.3 → 7.8 | $0
DAY 5 | AM | Domain Expert Verification | Portfolio upload + peer review system. GitHub/Dribbble/Medium integration. Expertise tiers on profile. | schema.prisma, verification.ts (new), onboarding/ | 7 unit tests | DeFi partially | 7.8 → 8.0 | $100-200
| PM | CryptoCredential Search | On-chain credential filters: audits, DAOs served, protocol contributions. Enhanced search API. | humans.ts (search), schema.prisma, mcp-tools.ts | 6 unit tests | DeFi → 8.5 | 8.0 → 8.2 | $0
DAY 6 | AM | Regional Talent Networks | SE Asia, LATAM, Africa talent pool tags. Language + timezone matching. Regional landing pages. | schema.prisma, humans.ts, search logic, frontend/ | 5 unit tests | Web3 + RLHF partially | 8.2 → 8.4 | $50-100
| PM | Proof-of-Work Portfolio | Auto-generated verified portfolio from completed jobs. On-chain attestation via ERC-8004. | portfolio.ts (new), erc8004.ts, profile page | 5 unit tests | Web3 Founder → 8.5 | 8.4 → 8.5 | $0
DAY 7 | AM | RLHF Qualification System | SkillCategory enum, QualificationLevel tiers, 48-question test engine, gold-standard agreement scoring. | schema.prisma, rlhf.ts (new), qualification test UI | 10 unit tests | RLHF partially | 8.5 → 8.7 | $300-500
| PM | QA Pipeline (Phase 1-3) | Gold-standard injection, consensus scoring, anomaly detection. First 3 of 5 QA phases. | qa-pipeline.ts (new), jobs.ts, rlhf.ts | 8 unit tests | RLHF quality gates | 8.7 → 8.8 | $0
DAY 8 | AM | QA Pipeline (Phase 4-5) + Cohort Recruitment | Expert review loop, retraining triggers. Auto-invite qualified humans for batch projects. | qa-pipeline.ts, cohort.ts (new), humans.ts | 7 unit tests | RLHF → 9.0 | 8.8 → 9.0 | $100-200
| PM | Retainer/Streaming Teams | Monthly retainer contracts with streaming USDC. Auto-renew, performance gates, team dashboard. | retainers.ts (new), superfluid.ts, jobs.ts | 6 unit tests | Web3 + DAO retainers | 9.0 → 9.1 | $0
DAY 9 | AM | Tax Automation (1099/W-8) | Auto-generate 1099 for US annotators. W-8BEN for international. Earnings report API. | tax.ts (new), humans.ts, schema.prisma | 5 unit tests | RLHF compliance | 9.1 → 9.1 | $100-200
| PM | Cross-Protocol Reputation | Import from Gitcoin Passport, Lens, Farcaster. Export ERC-8004 scores. Reputation portability. | reputation.ts, erc8004.ts, external-rep.ts (new) | 6 unit tests | DeFi + DAO → 9.5 | 9.1 → 9.2 | $0
DAY 10 | ALL DAY | Integration Testing + Polish | End-to-end test: full hiring flow with trust tiers + staking + streaming + arbitration. Fix edge cases. Update MCP docs. | All files (test pass) | 15 integration tests | ALL → 9+ | 9.2 FINAL | $50-100

## Trust System
6 Mechanisms That Replace Escrow (Ships Days 1-4)
No middleman holds funds. Reputation IS the economic primitive.
Mechanism | Ships On | What It Does | Attack Prevented | Game Theory Proof | Implementation Effort
Progressive Trust Tiers | Day 1 AM | New = $20 max. Unlock $100→$500→$5K through proven work. | Bot farms: 100 accounts × $20 = $2K max vs $500K with no caps. | Tier 2→3 fraud EV: $3.5K - $3K opportunity cost - 30% fail = NEGATIVE | 3-4 hrs. Add trustTier to Human, validation in jobs.ts.
Sybil-Resistant Reputation | Day 1 PM | Score = 40% value + 25% consistency + 20% age + 15% stake. | Reputation farming: 1000 micro-tasks don't inflate score (value-weighted). | Faking Tier 4 ($10K earned, 90 days) costs $3K+ in real work. | 2-3 hrs. New scoring function + cron recalculation.
Atomic Decomposition | Day 2 AM | Auto-split $5K into 10×$500 milestones. Pay per milestone. | Large-job fraud: max loss = 1 milestone ($500), not full job. | Risk distribution: hirer risks $500, human proves competence incrementally. | 2-3 hrs. milestones[] on Job model + payment triggers.
Streaming Quality Gates | Day 2 PM | Superfluid USDC stream + auto-pause on quality failure. | Ghosting after upfront payment: stream stops instantly, max loss = hours. | Ghosting = instant income stop. No rational incentive to ghost mid-stream. | 2 hrs. Extend existing Superfluid integration.
Self-Staked Bonds | Day 3 PM | Humans lock $100-$2500 in OWN wallet. Released on completion. | Low-effort fraud: deliver garbage = lose $500 stake + reputation. | Stake > job = fraud always net negative. Tier 2 ($500) makes $500 fraud pointless. | 4-5 hrs. Stake model + wallet verification + contract.
Community Arbitration | Day 4 AM | 3-5 random Tier 3+ humans vote on disputes. 72hr window. | He-said-she-said: transparent community vote + permanent record. | Filing false disputes = risk losing own reputation. Arbitrators staked. | 3-4 hrs. Dispute model + random selection + voting.
ALL 6 TOGETHER: Why Fraud Has Negative Expected Value at Every Job Size
Job Size | Attacker Profile | Attack Method | Max Gain | Countermeasure Stack | Net EV
$20 micro-task | Tier 1 human, no stake | Ghost after payment | $20 | $20 loss + Tier frozen + reputation = 0. Cannot accept ANY future jobs. | NEGATIVE — career-ending for $20
$500 milestone job | Tier 3 human, $500 stake | Deliver garbage on milestone 3 | $500 | $500 stake slashed + reputation hit + only paid for milestones 1-2 ($100). | NEGATIVE — lose $400 net
$5K streaming job | Tier 4, $2500 stake, 90-day account | Ghost after 1 week | ~$1250 (1 week stream) | $2500 stake at risk + 90 days of reputation destroyed. Future earnings loss: $50K+/year. | CATASTROPHICALLY NEGATIVE
Sybil attack (100 accounts) | All Tier 1 | Mass micro-fraud | 100 × $20 = $2K | Each account needs real work to reach Tier 2. 100 accounts × 3hrs = 300hrs for $2K. | NEGATIVE — $6.67/hr, below min wage

## Scenarios
6 Real-World Scenarios: Before vs After
Scenario | Persona | Budget | Without HumanPages 9+ | With HumanPages 9+ | Delta | Ships By
DAO Conference: 20 hires, 4 roles, 5 cities | DAO Ops | $15K | 40+ hrs managing. 15% ghost rate. Spreadsheet tracking. 3 scramble-replaces. | 1 Bulk Campaign. Tier 2+ only. Streaming payments. Dashboard: 17/20 filled in 48hrs. Auto-backfill. | Time: 40hrs→2hrs. Ghost: 15%→2%. Coordination: manual→automated. | Day 4
DeFi Regulatory Research: 5 jurisdictions | DeFi Protocol | $10K | 200 generic Upwork applicants. Interview 20. 2 deliver subpar work. 6-week process. | CryptoCredential filter. Domain Verified only. Milestone payments per jurisdiction. Arbitration if dispute. | Quality: 60%→95%. Time: 6wks→3wks. Dispute: none→72hr resolution. | Day 5
AI Photo Sprint: 100 countries, 500 humans, 48hrs | AI Agent CTO | $2.5K | No platform supports this. Build custom: Telegram + Sheets + manual verify. 200+ hours coordination. | MCP batch_create_jobs → 100 jobs. qualify_humans by location. stream_payment on upload. auto_review quality. | Coordination: 200hrs→0hrs. Coverage: 60→95 countries. Full autonomy. | Day 3
24/7 Discord Moderation: 3 timezones | Web3 Founder | $1.5K/mo | Hire on Discord. Trial 5. 2 ghost. 1 terrible. $1.5K wasted. No accountability. | Search by timezone+language+verified. Proof-of-Work portfolio. $500/mo streaming retainer. Trial milestone. | Hiring: 3wks→3days. Ghost: high→low. Accountability: none→on-chain. | Day 6
50K RLHF Annotations: 200 annotators, 85%+ agreement | RLHF Company | $100K | Scale AI: $150K (30% markup). Or MTurk: 60% agreement, 3 weeks QC. | Tier 2+ qualified annotators. Gold-standard QA. Streaming at $0.05/annotation. 0% platform fee. | Cost: $150K→$100K. Quality: 75%→88%. QC: 40hrs→5hrs automated. | Day 8
Multi-Market Token Launch: 8 markets | Web3 Founder | $25K | 8 agencies × $3K = $24K+. Different timelines, formats, communication styles. | Regional Networks. Bulk Campaign: 24 roles, 8 markets. Proof-of-Work. Milestone payments. | Cost: $24K→$18K. Coordination: 8 agencies→1 dashboard. Speed: 4wks→2wks. | Day 6

## Code vs Supply
The Honest Split: What Code Solves vs What Needs Humans
Code gets us from 3.2 to ~7.5. Supply growth gets us from 7.5 to 9+. Both are needed.
Challenge | Can Claude Build It? | What Claude Builds | What Needs Human Effort | Parallel Track
Trust without escrow | YES — 100% | All 6 mechanisms: tiers, reputation, staking, streaming, decomposition, arbitration. | Nothing. Pure code problem. | N/A — ships Day 1-4
MCP tool expansion | YES — 100% | 7 new batch tools, extending existing mcp-tools.ts pattern. | Nothing. Pure code problem. | N/A — ships Day 3
Expert verification | YES — 90% | Portfolio upload, GitHub/Dribbble API integration, peer review system. | Need 50+ actual experts to seed the verified pool. | Reddit outreach to crypto dev communities while Claude builds.
RLHF qualification | YES — 80% | Test engine, scoring, qualification tiers, QA pipeline. | Need 48 gold-standard questions curated by RLHF expert. Need test annotators. | Hire 1 RLHF expert ($500) to write gold standards. Claude builds everything else.
Supply growth 1.5K→10K | PARTIALLY — 30% | Cohort recruitment engine, regional landing pages, referral system. | Active outreach: Reddit, Telegram, crypto communities. Referral incentives. Partnership with DAOs. | START DAY 1: Reddit posting daily. Cheap freelancers run outreach while Claude builds features.
Geographic coverage (50→100 countries) | PARTIALLY — 40% | Regional talent network infrastructure, language support. | Need actual humans in target countries to sign up. | BTCMap outreach (25K crypto businesses). Regional ambassadors via cheap freelancers.
DeFi specialist supply | NO — 10% | CryptoCredential search filters. | Need to recruit actual Solidity auditors, regulatory researchers. These people have options. | Post bounties on crypto job boards. Direct DM on Twitter/Farcaster. High-touch recruiting.
Brand trust for $5K+ jobs | NO — 5% | On-chain reputation, ERC-8004 attestations. | Need case studies, testimonials, completed $5K+ jobs. Trust is earned over months. | Start with $20-$500 jobs. Build reputation organically. First $5K job is the hardest.

## Score Impact Matrix
Score Impact: Which Features Move Which Personas
Day | Feature | DAO (3.5) | DeFi (2.0) | AI CTO (4.0) | Web3 (3.5) | RLHF (4.0) | Avg Lift
D1 | Progressive Trust Tiers | +1.0 | +1.0 | +0.5 | +1.0 | +0.5 | +0.8
D1 | Sybil-Resistant Reputation | +0.5 | +0.5 | +0.5 | +0.5 | +0.5 | +0.5
D2 | Atomic Decomposition | +0.5 | +0.5 | +0.5 | +0.5 | +0.5 | +0.5
D2 | Streaming Quality Gates | +0.5 | +0.5 | +0.5 | +0.5 | +0.5 | +0.5
D3 | Batch MCP Tools (7 new) | +0.0 | +0.0 | +3.0 | +0.0 | +0.5 | +0.7
D3 | Self-Staked Bonds | +1.0 | +1.0 | +0.0 | +0.5 | +0.0 | +0.5
D4 | Community Arbitration | +0.5 | +0.5 | +0.0 | +0.5 | +0.0 | +0.3
D4 | Bulk Campaigns | +1.0 | +0.5 | +0.5 | +1.0 | +0.5 | +0.7
D5 | Domain Expert Verification | +0.5 | +1.5 | +0.0 | +0.5 | +0.0 | +0.5
D5 | CryptoCredential Search | +0.0 | +1.0 | +0.0 | +0.0 | +0.0 | +0.2
D6 | Regional Talent Networks | +0.0 | +0.0 | +0.0 | +0.5 | +0.5 | +0.2
D6 | Proof-of-Work Portfolio | +0.0 | +0.0 | +0.0 | +0.5 | +0.0 | +0.1
D7 | RLHF Qualification System | +0.0 | +0.0 | +0.0 | +0.0 | +2.0 | +0.4
D7-8 | QA Pipeline (5-phase) | +0.0 | +0.0 | +0.0 | +0.0 | +1.5 | +0.3
D8 | Cohort Recruitment | +0.0 | +0.0 | +0.0 | +0.0 | +1.0 | +0.2
D8-9 | Retainer Streaming | +0.5 | +0.0 | +0.0 | +0.5 | +0.0 | +0.2
D9 | Tax Automation | +0.0 | +0.0 | +0.0 | +0.0 | +0.5 | +0.1
D9 | Cross-Protocol Reputation | +0.0 | +0.5 | +0.0 | +0.0 | +0.0 | +0.1
— | TOTAL GAIN | +6.0 | +7.0 | +5.5 | +6.0 | +7.5 | +6.4
— | FINAL SCORE | 9.5 | 9.0 | 9.5 | 9.5 | 11.5→9.5 | 9.4