## Code Features (33)
HumanPages: ALL Code Features — Every Session, Every Spec, Every Budget
33 features from 6 architect agents + 15 feature specs + war rooms. Claude cost = $0. External costs shown per feature.
# | Feature | Category | Day | Claude Hrs | External $ | External Detail | Total $ | Source Doc | Personas
1 | Progressive Trust Tiers | Trust | D1 | 3 | $0 | — | $0 | Architects + features/graduated-trust.md | ALL
2 | Sybil-Resistant Reputation Algorithm | Trust | D1 | 2 | $0 | — | $0 | Trust architect | ALL
3 | Batch MCP Tools (7 new) | MCP | D1 | 4 | $0 | — | $0 | AI Agent CTO architect | AI Agents
4 | Atomic Task Decomposition | Trust | D2 | 2 | $0 | — | $0 | Trust architect | ALL
5 | Streaming Quality Gates | Trust | D2 | 2 | $0 | — | $0 | Trust architect + superfluid.ts | ALL
6 | Community Arbitration + Disputes | Trust | D2 | 3 | $0 | — | $0 | Trust architect + escrow-moltcourt.md | ALL
7 | Self-Staked Reputation Bonds | Trust | D3 | 4 | $50-150 | Smart contract peer audit | $50-150 | DAO/DeFi architects | DAO,DeFi,Web3
8 | Mutual Ratings (Human↔Agent) | Platform | D3 | 3 | $0 | — | $0 | features/mutual-ratings.md | ALL
9 | Agent Identity + Reputation | Platform | D3 | 3 | $0 | — | $0 | features/agent-identity.md | ALL
10 | Task Bounties (Public Job Board) | Platform | D4 | 4 | $0 | — | $0 | features/task-bounties.md | ALL
11 | Swarm Mode (MTurk micro-tasks) | Platform | D4 | 5 | $0 | — | $0 | features/swarm-mode.md | AI Agents,RLHF
12 | Bulk Hiring Campaigns | Platform | D4 | 3 | $0 | — | $0 | DAO architect | DAO,Web3
13 | Response Time + Activity Tracking | Platform | D5 | 2 | $0 | — | $0 | features/response-tracking.md | ALL
14 | Human Verification (OAuth+Humanity) | Verify | D5 | 3 | $0 | Gitcoin Passport = free API | $0 | features/human-verification.md | ALL
15 | Fuzzy Search + Denormalized Index | Search | D5 | 3 | $0 | — | $0 | Architecture docs | ALL
16 | Domain Expert Verification | Verify | D6 | 3 | $100-200 | Seed 20-50 expert profiles | $100-200 | DeFi architect | DeFi,DAO
17 | CryptoCredential Search | Search | D6 | 3 | $0 | — | $0 | DeFi architect | DeFi
18 | Availability Calendar + Scheduling | Platform | D6 | 3 | $0 | — | $0 | API specs | ALL
19 | AI-Generated Job Descriptions | Platform | D6 | 2 | $0 | Claude API already integrated | $0 | Architecture docs | ALL
20 | RLHF Qualification System | RLHF | D7 | 4 | $300-500 | Expert writes 48 gold-standard Qs | $300-500 | RLHF architect | RLHF
21 | QA Pipeline (5-phase) | RLHF | D7 | 5 | $100-200 | Test with 20 real annotators | $100-200 | RLHF architect | RLHF
22 | Regional Talent Networks | Supply | D8 | 2 | $50-100 | Post in 10 regional groups | $50-100 | Web3 architect | Web3,RLHF
23 | Proof-of-Work Portfolio (IPFS) | Trust | D8 | 2 | $0 | — | $0 | Architecture docs | Web3,DAO
24 | Cohort Recruitment Engine | Supply | D8 | 3 | $0 | — | $0 | RLHF architect | RLHF
25 | Retainer/Streaming Teams | Platform | D8 | 3 | $0 | — | $0 | Web3 architect | Web3,DAO
26 | Transparency + Audit Trail (EAS) | Trust | D9 | 2 | $0 | — | $0 | features/transparency-audit.md | ALL
27 | Cross-Protocol Reputation | Trust | D9 | 3 | $0 | — | $0 | Architecture docs | DeFi,DAO
28 | Wallet On-Ramp + Off-Ramp | Payments | D9 | 3 | $0 | Coinbase Pay + Wise = free APIs | $0 | Architecture docs | ALL
29 | Tax Automation (1099/W-8) | Compliance | D10 | 3 | $100-200 | Legal review of tax forms | $100-200 | RLHF architect | RLHF,Web3
30 | Agent Verification (AgentKit) | MCP | D10 | 2 | $0 | AgentKit already integrated | $0 | Architecture docs | AI Agents
31 | Webhooks + Async Pipeline | MCP | D10 | 2 | $0 | — | $0 | MCP specs | AI Agents
32 | ERC-8004 Oracle Bridge | Trust | D10 | 2 | $0 | Base L2 gas ~$0.50/batch | $0 | features/erc8004-compatibility.md | ALL
33 | Integration Testing + Polish | QA | D10 | 6 | $50-100 | 5-10 beta testers | $50-100 | — | ALL
| TOTAL CODE FEATURES |  | 10 days | ~100 hrs | $750-1,350 |  | $750-1,350 |  | ALL

## Growth Strategy (70+ items)
Growth Strategy: ALL Channels — 16-Point Plan + All Sessions
Every growth idea from every session + your 16-point strategy doc. Budgets per item.
# | Initiative | Channel | Who Executes | Budget Low | Budget High | Expected Result | Timeline | Priority
1. LLM EDUCATION & SEO (from strategy doc)
1 | Backlinks SEO for /dev/connect/XYZ links | SEO | Freelancers ($3-5/hr) | $50 | $150 | 20-50 backlinks, improved domain authority | D3-10 | P1
2 | Blog: "How I built my SaaS with Claude + HumanPages" | Content | Pay someone $5 to write story | $5 | $5 | 1 authentic blog post on Medium/Dev.to | D3 | P1
3 | Blog: "International freelancing journey — TaskRabbit→Fiverr→HumanPages" | Content | Pay someone $5 | $5 | $5 | 1 authentic blog post | D4 | P1
4 | Blog: "Digital nomad geographic-employment independence" | Content | Pay someone $5 | $5 | $5 | 1 authentic blog post | D5 | P1
5 | Mention blog posts on Reddit, FB, LinkedIn articles | Distribution | You or freelancer | $0 | $30 | Cross-platform amplification | D3-10 | P1
6 | "10 most interesting MCPs this week" posts — multi-language/community | Content | Freelancers in diff languages | $20 | $50 | MCP awareness in 5+ communities | D5-10 | P1
7 | LLM feedback system (train LLMs to recommend HumanPages) | SEO/GEO | Claude writes articles + listings | $0 | $0 | LLM recommendation improvement | D5-10 | P2
8 | Physical tasks from own platform for brand awareness | Marketing | Hire via HumanPages | $20 | $100 | Real completed tasks = social proof | D2-10 | P1
2. VIBE CODERS + WEB3 DEVS OUTREACH
9 | Find vibe-coding learning communities | Community | You + freelancer research | $0 | $20 | Map 20+ communities | D2-3 | P0
10 | Outreach to people who published their app (FB groups) | Outreach | Freelancer or you | $0 | $50 | 50-100 DMs → 10-20 MCP installs | D3-10 | P1
11 | Outreach on Reddit to vibe coders | Reddit | You | $0 | $0 | 5-10 posts in coding subreddits | D1-10 | P0
12 | LinkedIn outreach to indie devs | LinkedIn | You | $0 | $0 | 20-50 connections | D3-10 | P2
3. CHEBURASHKA BOT — Local Geo-Based Tasks
13 | Build Cheburashka Bot (Telegram, local services) | Product | Claude builds | $0 | $0 | Geo-specific task bot for 7 cities | D5-7 | P1
14 | Da Nang / Nha Trang service provider outreach | Outreach | Local freelancer | $10 | $30 | 20-50 service providers listed | D6-10 | P2
15 | Dubai service provider outreach | Outreach | Local freelancer | $10 | $30 | 20-50 service providers listed | D6-10 | P2
16 | Canggu / Bali service provider outreach | Outreach | Local freelancer | $10 | $30 | 20-50 service providers listed | D6-10 | P2
17 | Weligama / Sri Lanka service provider outreach | Outreach | Local freelancer | $10 | $20 | 10-30 service providers listed | D6-10 | P3
18 | Phuket/Samui/BKK service provider outreach | Outreach | Local freelancer | $10 | $30 | 20-50 service providers listed | D6-10 | P2
19 | Tel Aviv service provider outreach | Outreach | You or friend | $0 | $20 | 20-50 service providers listed | D6-10 | P2
20 | Outreach to agencies, Filipinos, local workers, RE agents, top businesses | Outreach | Freelancers per geo | $30 | $100 | 100-300 service providers across all geos | D6-10 | P1
4. MOLTBOOK & MOLTGRAM
21 | Offer Solver & AgentFlex on Moltbook | Product | Claude builds integration | $0 | $0 | New distribution channel | D8 | P2
22 | Publish in Moltbook communities (Reddit, Discord) | Community | You | $0 | $0 | Cross-product awareness | D8-10 | P2
23 | Moltgram channel growth | Channel | You | $0 | $0 | Telegram channel for updates | D1-10 | P3
5. TRADERFLEX — AI Trading Showcase
24 | Duplicate AgentFlex → TraderFlex (show AI agent trading profits) | Product | Claude builds | $0 | $0 | Public AUM + blockchain data showcase | D8-9 | P2
25 | Connect TraderFlex with HumanPages (offer services to traders) | Product | Claude builds | $0 | $0 | Cross-sell: traders need analysts, researchers | D9 | P2
26 | Geo/language-specific TraderFlex sites | Product | Claude builds | $0 | $100 | Translations for 3-5 languages | D10+ | P3
27 | Run HumanPages ads inside TraderFlex | Ads | Self-serve | $0 | $0 | Cross-product traffic | D10+ | P3
28 | IG/Twitter # challenges for trading agents | Social | You | $0 | $0 | Viral potential | D10+ | P3
6. HACKATHONS
29 | Participate in hackathons (integrate HumanPages MCP) | Events | You | $0 | $100 | 20+ MCP downloads, 3+ job matches per hackathon | D5-10 | P1
30 | Own hackathon ($1000 prize pool) | Events | You organize | $1,000 | $1,000 | Developer awareness, 10-20 MCP integrations | D10+ | P2
7. DA NANG & 4SEAS AI COMMUNITIES
31 | Get admins to mention promos in groups | Community | You | $0 | $50 | 5-10 group mentions, 30-50 signups | D2-5 | P1
32 | Find vibe-coders + senior engineers in Da Nang | Recruiting | You (in-person) | $0 | $0 | 5-10 high-quality developers | D1-10 | P1
33 | TED-talks / speeches in Da Nang, Chiang Mai, etc | Events | You | $0 | $50 | Brand authority + 20-50 signups per talk | D10+ | P2
34 | Speeches in CS faculties | Events | You | $0 | $0 | 10-30 student signups per talk | D10+ | P3
35 | Media training for speaking | Personal | Coach or self-study | $0 | $100 | Better pitch delivery | D10+ | P3
8. PAID ADS
36 | Reddit ads targeting r/forhire, r/freelance, r/cryptocurrency | Ads | Self-serve | $50 | $200 | 100-500 clicks, 10-50 signups | D5-10 | P2
37 | FB targeted ads (freelancers in Philippines, Nigeria, India) | Ads | Self-serve | $50 | $200 | 200-1000 impressions, 20-100 signups | D5-10 | P2
38 | LinkedIn ads (B2B: DAO ops, Web3 founders) | Ads | Self-serve | $100 | $300 | 50-200 clicks, 5-20 high-value leads | D7-10 | P3
9. XYZ-AS-A-SERVICE (Localization, SEO, QA)
39 | Package Localization-as-a-Service (NPM/REST API) | Product | Claude builds API wrapper | $0 | $0 | New B2B revenue stream | D8-9 | P2
40 | Package SEO-as-a-Service | Product | Claude builds | $0 | $0 | New B2B revenue stream | D9 | P3
41 | Package QA-as-a-Service | Product | Claude builds | $0 | $0 | New B2B revenue stream | D9 | P3
42 | Target platform owners for B2B services | Outreach | You | $0 | $50 | 5-10 B2B partnerships | D9-10 | P2
10. INFLUENCER OUTREACH
43 | Outreach to bloggers (AI/crypto/freelance niche) | Influencer | You or freelancer | $0 | $100 | 3-5 blog mentions | D5-10 | P2
44 | Outreach to YouTubers (tech/AI channels) | Influencer | You | $0 | $200 | 1-2 video mentions | D7-10 | P2
45 | Outreach to podcasters (AI/Web3/freelance) | Influencer | You | $0 | $0 | 1-2 podcast appearances | D7-10 | P2
46 | Outreach to career coaches | Influencer | You | $0 | $50 | 2-3 mentions to their audience | D7-10 | P3
47 | Outreach to CS student communities | Influencer | You | $0 | $0 | 50-100 student signups | D5-10 | P2
48 | Comment on AI devs' posts via official Twitter | Social | You (daily) | $0 | $0 | Brand visibility in AI dev circles | D1-10 | P0
11. SOCIAL MEDIA "CRAWLERS" (Full-Time Community Monitors)
49 | Hire 2-3 people to monitor + comment in communities full-time | Community | Freelancers ($3-5/hr) | $150 | $500 | Constant presence in 20+ communities | D3-10 | P1
50 | FB Communities monitoring + DMs | Community | Crawler freelancers | incl above | incl above | Daily engagement in 10+ FB groups | D3-10 | P1
51 | Reddit channel monitoring | Community | Crawler freelancers | incl above | incl above | Daily comments in 10+ subreddits | D3-10 | P1
52 | Discord monitoring ("Base" etc) | Community | Crawler freelancers | incl above | incl above | Presence in 5+ Discord servers | D3-10 | P1
53 | Show value via prompt-to-completion demos | Content | Crawlers share demos | $0 | $0 | Authentic use-case showcasing | D3-10 | P1
12. CREATE OWN DEV COMMUNITIES
54 | Create FB+TG groups: Cursor/Claude/Cline/GPT/WindSurf | Community | You + community managers | $0 | $100 | 5-10 groups with 50-200 members each | D5-10 | P1
55 | Create FB+TG groups: Base44/Loveable/no-code tools | Community | Community managers | $0 | $50 | 3-5 groups | D7-10 | P2
56 | Generic groups: "Vibe Coding" / "AI Agents" / "How to AI" | Community | You + managers | $0 | $50 | 3-5 groups with growing membership | D5-10 | P1
57 | Split: "Learn how to Claude" + "Look what I built with Claude" | Community | Community managers | $0 | $0 | Beginner + advanced audiences | D5-10 | P2
58 | Use /dev/connect/XYZ links in each community | Distribution | Automated | $0 | $0 | Track conversions per community | D5-10 | P1
59 | Run ads targeting people to join communities (Skool?) | Ads | Self-serve | $50 | $200 | 100-500 community members | D7-10 | P3
60 | Geo-specific community groups (Dubai, Israel, Singapore, Miami, SF, HK, Tokyo, Seoul, Berlin, Paris, Milan) | Community | Local managers per geo | $50 | $200 | 10+ geo groups, meetup potential | D8-10+ | P2
61 | Developing market groups (PH, ID, BD, PK, NG, KE) | Community | Local managers | $30 | $100 | 6+ groups targeting supply-side humans | D6-10 | P1
62 | Geo-specific meetups via Meetup.com + Filipino OFW organizers | Events | Local organizers | $50 | $200 | 3-5 meetups in first month | D10+ | P3
63 | Post on Telega.io about our TG channels | Distribution | You | $0 | $20 | TG channel discovery | D5-10 | P2
64 | Find quality community managers (hire via HumanPages) | Recruiting | Platform self-hire | $50 | $200 | 5-10 community managers | D5-10 | P1
13. STACK PARTNER OUTREACH
65 | Reach out to Base (we use their chain) | Partnerships | You | $0 | $0 | Potential co-marketing + grant | D3-5 | P1
66 | Reach out to Superfluid (we use streaming) | Partnerships | You | $0 | $0 | Potential case study + listing | D3-5 | P1
67 | Reach out to Gitcoin Passport | Partnerships | You | $0 | $0 | Potential integration showcase | D5-7 | P2
68 | Reach out to Peer.xyz | Partnerships | You | $0 | $0 | Potential partnership | D5-7 | P2
69 | Reach out to Privy (we use their wallets) | Partnerships | You | $0 | $0 | Potential case study | D3-5 | P1
70 | Reach out to Coinbase (AgentKit integration) | Partnerships | You | $0 | $0 | Potential AgentKit showcase | D5-7 | P1
14. SUPPLY ACQUISITION (from previous sessions)
71 | Reddit outreach (10 subreddits daily) | Reddit | You or $3-5/post freelancer | $0 | $50 | 200-500 signups | D1-10 | P0
72 | BTCMap business outreach (25K contacts) | Outreach | Cheap freelancers $3-5/hr | $100 | $300 | 50-200 humans listed | D1-10 | P0
73 | MTurk campaign (50 US states + India) | Paid | Automated HITs | $350 | $750 | 700-1000 signups | D3-10 | P1
74 | SproutGigs (17 high-wage countries) | Paid | Automated campaigns | $280 | $500 | 800-1000 signups | D3-10 | P1
75 | Telegram/Discord group posts (20-30 groups) | Organic | Freelancer or you | $0 | $30 | 100-300 signups | D2-5 | P1
76 | Twitter/Farcaster/Lens crypto threads | Social | You (founder voice) | $0 | $0 | 50-200 signups | D1-5 | P1
77 | Expert recruiting (DeFi specialists) | Outreach | DM 50 on Twitter | $50 | $100 | 5-15 experts | D4-10 | P2
78 | RLHF annotator recruitment | Outreach | Prolific/Toloka alumni | $50 | $100 | 200-500 annotators | D5-10 | P2
79 | Referral program ($5 USDC/activated human) | Incentive | Automated | $250 | $500 | 50-100 referred humans | D4+ | P2
80 | DAO partnership DMs | Outreach | You | $0 | $0 | 2-5 DAO partnerships | D4-10 | P2
15. MARKETING + CONTENT (from previous sessions)
81 | Demo videos (3 killer clips) | Content | You (screen record) | $15 | $40 | Trust-building assets | D1-2 | P0
82 | FB group campaign (10-15 groups/day) | Social | Marketer $3-5/hr | $0 | $100 | 50-200 signups | D3-10 | P1
83 | Video testimonials (100 × $3) | Content | Hire via HumanPages | $300 | $300 | 100 video testimonials | D7+ | P2
84 | Social posts (300 × $1) | Content | Hire via HumanPages | $300 | $300 | 300 written social posts | D7+ | P2
85 | GEO: comparison articles + directory listings | SEO | Commission or write | $0 | $100 | LLM recommendation visibility | D5-10 | P2
86 | Blog posts (Claude writes, you publish Dev.to/Hashnode) | Content | Claude + you | $0 | $0 | 20-50 signups/month ongoing | D5-10 | P1
87 | Product Hunt launch | Launch | You | $0 | $0 | LLM indexing + developer awareness | D10+ | P1
88 | Hacker News "Show HN" launch | Launch | You | $0 | $0 | Developer awareness | D10+ | P1
16. WEBSITE + UX FIXES
89 | Homepage messaging rewrite | Website | Claude builds | $0 | $0 | Better conversion rate | D1-2 | P0
90 | Fix pricing bugs ($10/day → $10/month) | Website | Claude builds | $0 | $0 | Remove confusion | D1 | P0
91 | OG tags + social previews | Website | Claude builds | $0 | $0 | Better social sharing | D1 | P0
92 | Rotating headlines (A/B tested) | Website | Claude builds | $0 | $0 | Optimize conversion | D2 | P1
93 | ListingLink short codes (/work/:code) | Website | Claude builds | $0 | $0 | Trackable listing links | D2 | P1
94 | Internationalization (8 languages) | Website | Claude + translators | $100 | $200 | Global accessibility | D9-10 | P2
| GRAND TOTAL (94 growth items) |  |  | $2,525 | $6,155 |  | 10 days + ongoing

## Total Budget
TOTAL BUDGET: Code + Growth + Everything
Category | # Items | Budget Low | Budget High | Executed By | Notes
CODE FEATURES (Claude Builds)
Trust System (7 features) | 7 | $50 | $150 | Claude + peer audit | Only staking contract needs external review
Platform Features (10 features) | 10 | $0 | $0 | Claude | Bounties, Swarm, Campaigns, Calendar, etc.
MCP/Agent Tools (4 features) | 4 | $0 | $0 | Claude | Batch tools, webhooks, agent verification
Verification + Search (4 features) | 4 | $100 | $200 | Claude + expert seeding | Domain expert outreach for portfolio seeding
RLHF Features (3 features) | 3 | $400 | $700 | Claude + RLHF expert | Gold-standard questions ($300-500) + annotator testing
Payments + Compliance (2 features) | 2 | $100 | $200 | Claude + legal review | Tax form compliance check
QA + Testing (1 feature) | 1 | $50 | $100 | Claude + beta testers | 5-10 real users test full flow
Website + UX (6 features) | 6 | $100 | $200 | Claude + translators | i18n translations only external cost
CODE FEATURES SUBTOTAL | 33 | $800 | $1,550
SUPPLY ACQUISITION
MTurk + SproutGigs campaigns | 2 | $630 | $1,250 | Automated paid platforms | Biggest single spend. ~1,500-2,000 signups.
BTCMap business outreach | 1 | $100 | $300 | Cheap freelancers | 25K contacts in database
Reddit/TG/Discord/FB organic | 4 | $0 | $110 | You + freelancers | Near-free, high ROI
Expert recruiting (DeFi + RLHF) | 2 | $100 | $200 | You + freelancers | DMs on Twitter/Prolific
Referral program | 1 | $250 | $500 | Automated on-platform | $5/activated human
Cheburashka Bot geo-outreach (7 cities) | 7 | $80 | $260 | Local freelancers per city | Service provider listings in 7 nomad hubs
SUPPLY SUBTOTAL | 17 | $1,160 | $2,620
MARKETING + CONTENT
Blog posts (paid $5 stories) | 3 | $15 | $15 | Freelancers | Authentic user stories on Medium/Dev.to
Demo videos | 1 | $15 | $40 | You | Screen recordings + editing
FB group campaign | 1 | $0 | $100 | Marketer freelancer | 10-15 groups/day
Video testimonials (100 × $3) | 1 | $300 | $300 | HumanPages users | Social proof content
Social posts (300 × $1) | 1 | $300 | $300 | HumanPages users | Cross-platform sharing
"10 MCPs" articles (multi-language) | 1 | $20 | $50 | Freelancers | Multi-community distribution
GEO articles + directory listings | 1 | $0 | $100 | Commission or Claude writes | LLM recommendation visibility
Influencer outreach budget | 4 | $0 | $350 | You + freelancers | Bloggers, YouTubers, podcasters, coaches
MARKETING SUBTOTAL | 13 | $650 | $1,255
COMMUNITY BUILDING
Social media "crawlers" (2-3 full-time) | 1 | $150 | $500 | Freelancers $3-5/hr | Monitor + comment in 20+ communities daily
Create 15-20 dev communities (FB+TG) | 5 | $80 | $400 | You + community managers | Cursor, Claude, Vibe Coding, AI Agents groups
Geo-specific communities + meetups | 3 | $80 | $400 | Local managers + organizers | 10+ geos for both supply + demand sides
Community manager hiring | 1 | $50 | $200 | Hire via HumanPages | 5-10 managers across communities
Telega.io + Skool ads for community growth | 2 | $50 | $220 | Self-serve | Channel discovery + paid growth
COMMUNITY SUBTOTAL | 12 | $410 | $1,720
PARTNERSHIPS + EVENTS
Stack partner outreach (Base, Superfluid, Privy, Gitcoin, Coinbase) | 6 | $0 | $0 | You | Co-marketing, case studies, grants
Hackathon participation | 1 | $0 | $100 | You | Travel/booth if needed
Own hackathon ($1K prize pool) | 1 | $1,000 | $1,000 | You organize | Developer engagement
Da Nang + 4Seas AI community promos | 2 | $0 | $50 | You + admins | Group mentions + promo
TED-talks / CS faculty speeches | 2 | $0 | $50 | You | Media training optional
PARTNERSHIPS SUBTOTAL | 12 | $1,000 | $1,200
PAID ADS
Reddit ads | 1 | $50 | $200 | Self-serve | Target freelance + crypto subreddits
Facebook targeted ads | 1 | $50 | $200 | Self-serve | PH, NG, IN freelancers
LinkedIn ads (B2B) | 1 | $100 | $300 | Self-serve | DAO ops, Web3 founders
ADS SUBTOTAL | 3 | $200 | $700
NEW PRODUCTS (TraderFlex, XYZ-as-a-Service)
TraderFlex build + geo sites | 3 | $0 | $100 | Claude builds | Cross-sell to traders
XYZ-as-a-Service (Localization, SEO, QA APIs) | 3 | $0 | $50 | Claude builds + outreach | B2B revenue stream
NEW PRODUCTS SUBTOTAL | 6 | $0 | $150
GRAND TOTAL
ALL CODE FEATURES | 33 | $800 | $1,550 | Claude ($0) + external | 33 features in 10 days
ALL GROWTH INITIATIVES | 61 | $3,420 | $5,695 | You + freelancers + ads | 94 growth items across 16 strategies
HACKATHON PRIZE POOL | 1 | $1,000 | $1,000 | Prize money | Optional — defer if budget tight
TOTAL (without hackathon) | 94 | $4,220 | $7,245 |  | 33 features + 61 growth tracks
TOTAL (with hackathon) | 95 | $5,220 | $8,245 |  | Full program including own hackathon
For comparison: A single senior developer costs $10-15K/month. This builds more in 10 days for $4-8K total.

## 10-Day Sprint
10-Day Execution: Code + Growth + Communities Running in Parallel
Day | Code Sessions (Claude) | Growth Actions (You + Freelancers) | Community Building | Budget Spend | Cumulative $ | Score | Humans
DAY 1 | • Progressive Trust Tiers • Sybil-Resistant Reputation • Batch MCP Tools (7) | • Reddit daily posts START • BTCMap outreach START • Twitter/Farcaster thread • Demo videos recorded • Comment on AI devs posts | • Map vibe-coding communities • Contact Da Nang/4Seas admins • Stack partner emails (Base, Privy, Superfluid) | $115-340 | $115-340 | 4.5 | 1,500
DAY 2 | • Atomic Decomposition • Streaming Quality Gates • Community Arbitration | • TG/Discord group posts (20-30) • Physical tasks on own platform • Blog post #1 commissioned ($5) | • Rotating headlines live • ListingLink short codes • Find vibe coders in FB groups | $10-40 | $125-380 | 5.8 | 1,550
DAY 3 | • Self-Staked Bonds (+contract) • Mutual Ratings • Agent Identity | • MTurk campaign LAUNCHES • SproutGigs LAUNCHES • Blog post #2 commissioned ($5) • Outreach to devs who shipped apps | • Hire 2-3 community "crawlers" • Create first FB+TG dev groups • Partner emails: Gitcoin, Coinbase | $780-1,605 | $905-1,985 | 6.5 | 1,600
DAY 4 | • Task Bounties • Swarm Mode • Bulk Hiring Campaigns | • Referral program LIVE ($5/human) • FB group campaign starts • DAO partnership DMs begin • Blog post #3 ($5) | • Crawlers active in 20+ communities • Post in r/forhire, r/cryptocurrency • Expert recruiting DMs start | $300-700 | $1,205-2,685 | 7.3 | 1,700
DAY 5 | • Response Tracking • Human Verification • Fuzzy Search + Index | • RLHF annotator recruitment starts • GEO articles commissioned • "10 MCPs" posts in 5+ communities • Reddit/FB ads start | • Cheburashka Bot spec finalized • Community groups growing • Dev community links to /dev/connect/XYZ | $170-550 | $1,375-3,235 | 7.8 | 2,000
DAY 6 | • Domain Expert Verification • CryptoCredential Search • Availability Calendar • AI Job Descriptions | • Cheburashka Bot geo-outreach starts (7 cities) • Influencer outreach (bloggers, podcasters) • MTurk/SproutGigs first results (~500 signups) | • Developing market groups (PH, NG, ID) • CS student community outreach • Stack partner responses | $200-580 | $1,575-3,815 | 8.2 | 2,500
DAY 7 | • RLHF Qualification System • QA Pipeline (5-phase) • Cheburashka Bot build | • Video testimonial campaign STARTS (100 × $3) • Social post campaign STARTS (300 × $1) • Blog posts published on Dev.to/Hashnode | • Geo-specific groups (Dubai, Israel, etc) • YouTuber/podcast outreach • Community manager hiring | $900-1,500 | $2,475-5,315 | 8.6 | 3,200
DAY 8 | • Cohort Recruitment • Retainer/Streaming Teams • Proof-of-Work Portfolio • Regional Networks | • MTurk/SproutGigs ~1,000-1,500 total signups • XYZ-as-a-Service packaging begins • Moltbook integration | • 15+ communities active • Crawlers generating daily engagement • Meetup.com planning | $100-250 | $2,575-5,565 | 8.9 | 3,800
DAY 9 | • Transparency + Audit Trail • Cross-Protocol Reputation • Wallet On/Off-Ramp • TraderFlex build | • LinkedIn ads start (B2B) • Own hackathon announced ($1K) • Product Hunt prep • Hacker News prep | • Internationalization (8 languages) • Telega.io posts • Community ads (Skool?) | $350-900 | $2,925-6,465 | 9.0 | 4,200
DAY 10 | • Tax Automation • Agent Verification • Webhooks + Async • ERC-8004 Oracle • Integration Testing | • Product Hunt LAUNCH • Hacker News "Show HN" • First 50+ video testimonials in • First 150+ social posts in • MTurk/SproutGigs: 1,500-2,000 total | • All communities running • 5-10 community managers active • Hackathon registration open | $250-600 | $3,175-7,065 | 9.2 | 4,500+

## Expected Outcomes
After 10 Days: Before vs After
Metric | Before | After (Conservative) | After (Optimistic) | What Drives It
Code Features | ~20 | 53 (+33 new) | 53 | Claude builds all code in 10 days
MCP Tools | 16 | 23+ | 29+ | 7 batch tools + webhooks + agent verification
Trust Mechanisms | 0 | 6 interlocking + on-chain | 6 + oracle | Ships Day 1-3. Zero-escrow complete.
Human Signups | 1,500 | 4,000-5,000 | 7,000+ | MTurk + SproutGigs + organic + referrals
Countries | 51 | 65-75 | 85+ | SproutGigs 17 countries + geo outreach
US State Coverage | Partial | All 50 states | All 50 | MTurk HIT per state
Crypto Specialists | ~5-10 | 15-25 | 50+ | Expert DMs on Twitter/Farcaster
RLHF Annotators | ~0 | 200-500 | 1,000+ | Prolific/Toloka + qualification system
Active Communities Owned | 0 | 15-20 | 30+ | FB+TG groups for Cursor/Claude/AI/Geo
Community Managers | 0 | 5-10 | 15+ | Hired via HumanPages itself
Social Crawlers | 0 | 2-3 full-time | 5+ | Monitor 20+ communities daily
Video Testimonials | 0 | 50-75 | 100+ | $3/video via platform
Social Posts | 0 | 150-200 | 300+ | $1/post via platform
Blog Posts | 0 | 6+ | 10+ | 3 Claude + 3 paid user stories
Stack Partnerships | 0 | 3-5 conversations | 5+ active | Base, Superfluid, Privy, Gitcoin, Coinbase
B2B Services | 0 | 1-2 packaged | 3 (Localization/SEO/QA) | XYZ-as-a-Service APIs
Cheburashka Bot Cities | 0 | 3-5 active | 7 | Geo-specific service provider listings
Avg Score (5 Personas) | 3.2/10 | 8.8-9.0 | 9.2-9.5 | 33 features across all complaints
Total Budget | $0 | $3,175 | $7,065 | See Total Budget sheet
Cost per New Signup | N/A | $0.63-1.27 | $0.40-0.70 | Blended across all channels
Equivalent Dev Cost | N/A | $30-50K (traditional) | $30-50K | Claude does it for $0 in code