## Master Priority
HumanPages: Unified Product Roadmap to 9+/10 Across All Sectors
Features ranked by cross-sector impact. Checkmarks show which sectors each feature unblocks.
# | Feature | Phase | Effort | Real Est. | Insurance | E-Comm | Research | Legal | Logistics | Marketing | AI Agents | Impact | Est. ARR | Dependencies
1 | Escrow + Dispute Resolution | P1 | 6-8 wks | Y | Y | Y | Y | Y | Y | Y | Y | CRITICAL | $3-8M | Smart contract audit
2 | Fiat Payment Rails (Wise/ACH/SEPA) | P1 | 8-10 wks | Y | Y | Y | Y | Y | Y | Y | Y | CRITICAL | $3-5M | Banking partner
3 | KYC/AML + Background Checks | P1 | 6-8 wks | Y | Y | Y | Y | Y | Y | Y | Y | CRITICAL | $2-4M | Identity provider (Checkr/Onfido)
4 | SLA Tiers + Auto-Refund Guarantees | P1 | 4-6 wks | Y | Y | Y | ~ | Y | Y | Y | Y | HIGH | $1-3M | Escrow (for refunds)
5 | Geofencing + Proof-of-Location | P1 | 3-4 wks | Y | Y | Y | Y | ~ | Y | ~ | Y | HIGH | $1-2M | Mobile app or EXIF parsing
6 | Portfolio Gallery + Work Samples | P2 | 2-3 wks | ~ | ~ | Y | ~ | ~ | ~ | Y | Y | HIGH | $1-2M | File storage (S3)
7 | Immutable Audit Trail (7-10yr) | P2 | 2-3 wks | ~ | Y | ~ | Y | Y | ~ | ~ | ~ | HIGH | $500K-2M | Hash-chain logging
8 | IP/Work-for-Hire Templates | P2 | 2 wks | ~ | ~ | Y | ~ | Y | ~ | Y | ~ | MEDIUM | $500K-1M | Legal counsel
9 | Bulk/Batch Job API | P2 | 1-2 wks | ~ | ~ | Y | Y | ~ | Y | Y | Y | MEDIUM | $500K-1M | Listings API (exists)
10 | Webhooks + Async Callbacks | P2 | 1.5 wks | ~ | Y | Y | ~ | ~ | Y | ~ | Y | MEDIUM | $300K-800K | None
11 | Institutional Billing (PO/Net-30) | P2 | 3 wks | ~ | Y | ~ | Y | Y | Y | Y | ~ | MEDIUM | $500K-2M | Stripe Invoicing
12 | IRB Compliance Templates | P2 | 4 wks | ~ | ~ | ~ | Y | ~ | ~ | ~ | ~ | NICHE | $500K-1M | Legal/ethics review
13 | Industry Integrations (MLS/TMS/Shopify) | P3 | 12-16 wks | Y | ~ | Y | ~ | ~ | Y | ~ | ~ | MEDIUM | $1-3M | Partner APIs
14 | Real-Time GPS Task Tracking | P3 | 3 wks | ~ | Y | ~ | ~ | ~ | Y | ~ | ~ | MEDIUM | $300K-1M | Mobile app
15 | Human Availability Calendar | P3 | 1.5 wks | ~ | ~ | Y | ~ | ~ | Y | Y | Y | MEDIUM | $300K-800K | Frontend work
16 | Compliance/Audit Dashboard | P3 | 4-6 wks | ~ | Y | ~ | Y | Y | ~ | ~ | ~ | MEDIUM | $500K-2M | Audit trail (row 7)
17 | On-Chain Reputation NFTs (ERC-8004) | P3 | 3-4 wks | ~ | ~ | ~ | ~ | ~ | ~ | ~ | Y | LOW | $200K-500K | ERC-8004 (partial)
18 | Team Collaboration (Multi-Seat) | P3 | 3 wks | ~ | ~ | ~ | Y | ~ | ~ | Y | ~ | LOW | $300K-800K | Auth system update
19 | AI Job Description Generator | P3 | 1 wk | ~ | ~ | Y | ~ | ~ | ~ | Y | Y | LOW | $100K-300K | LLM API
20 | Analytics Dashboard | P3 | 2-3 wks | ~ | Y | Y | ~ | ~ | Y | Y | ~ | LOW | $200K-500K | Data warehouse
Legend: | Y = Critical for sector ¦ ~ = Nice-to-have ¦ P1 = Phase 1 (Weeks 1-10) ¦ P2 = Phase 2 (Weeks 8-16) ¦ P3 = Phase 3 (Weeks 14-24)

## Phase Timeline
Implementation Phases — 24-Week Master Plan
Phase | Timeline | What Ships | Score After | Cumulative ARR Unlock
Phase 0: Foundation | Week 1-2 | Escrow smart contract audit, KYC provider selection, Wise API keys, legal templates drafted | 5.5/10 (prep only) | $0
Phase 1: Trust Layer | Week 2-10 | Escrow + Dispute Resolution, Fiat Payments (Wise), KYC/AML + Background Checks, SLA Tiers, Geofencing | 8.0/10 | $8-15M potential
Phase 2: Enterprise Ready | Week 8-16 | Portfolio Gallery, Audit Trail, IP Templates, Bulk API, Webhooks, Institutional Billing, IRB Templates | 9.0/10 | $12-22M potential
Phase 3: Market Leader | Week 14-24 | Industry Integrations (MLS/TMS/Shopify), GPS Tracking, Availability Calendar, Compliance Dashboard, Reputation NFTs, Team Collab, AI Job Gen, Analytics | 9.5+/10 | $15-30M potential

## Score Projections
Projected Scores After Each Phase
Sector | Current | After P1 | After P2 | After P3
Real Estate | 5 | 7.5 | 8.5 | 9.2
Insurance | 5 | 7.5 | 8.5 | 9.2
E-Commerce | 6 | 8 | 9 | 9.7
Research/Academia | 6.5 | 8 | 9 | 9.2
Legal/Compliance | 5 | 7.5 | 8.5 | 9
Logistics | 5.5 | 7.5 | 8.5 | 9.5
Marketing/Media | 6 | 7.5 | 9 | 9.5
AI/Agent Platforms | 5 | 8 | 9 | 9.5
AVERAGE | 5.5 | 7.6875 | 8.75 | 9.35

## Investment
Investment Required & Expected Returns
Category | Phase 1 | Phase 2 | Phase 3 | Notes
Engineering (FTE-months) | 12-16 FTE-mo | 8-10 FTE-mo | 10-14 FTE-mo | 3-4 backend + 1-2 frontend + 1 Solidity + 1 DevOps
External Services | $30-50K | $15-25K | $20-30K | KYC provider, smart contract audit, legal review, Wise setup
Timeline | 8-10 weeks | 6-8 weeks | 8-10 weeks | Phases overlap by 2-4 weeks; total ~20-24 weeks
Total Cash Cost | $150-200K | $80-120K | $100-150K | Assumes $12-15K/FTE-month fully loaded
RETURNS | Phase 1 | Phase 2 | Phase 3
Avg Sector Score | 7.6/10 | 8.8/10 | 9.4/10 | From 5.5 average today
Enterprise-Ready Sectors | 3 of 8 | 6 of 8 | 8 of 8 | Score >= 8.5 = enterprise-ready
Est. ARR Unlock | $8-15M | $12-22M | $15-30M | Cumulative addressable across all sectors
Payback Period | 6-9 months | 3-5 months | 2-4 months | Based on first 3-5 enterprise deals

## 5 Non-Negotiables
The 5 Features That Every Single Sector Demands
Build these first. Everything else is optional until these ship.
# | Feature | Why Every Sector Needs It | Effort | Score Impact
1 | Escrow + Dispute Resolution | Without escrow, no sector trusts jobs >$200. Insurance can't verify claims. Legal can't hold evidence funds. E-commerce can't guarantee photography. Every evaluator flagged this as blocker #1. | 6-8 weeks | +2.0 points avg
2 | Fiat Payment Rails | Corporate treasury departments cannot send USDC. Period. This blocks every enterprise deal. Humans in developing countries need local currency withdrawal. Wise/ACH/SEPA integration 5x's the human supply overnight. | 8-10 weeks | +1.0 points avg
3 | KYC/AML + Background Checks | Insurance requires OFAC screening. Legal requires identity verification. Research requires IRB-grade participant tracking. Logistics requires driver verification. No regulated industry can use unverified humans. | 6-8 weeks | +1.5 points avg
4 | SLA Guarantees + Auto-Refund | Logistics needs 2-4h response commitment. Insurance needs claims turnaround. E-commerce needs photography deadlines. Advisory commitments aren't enough — binding SLAs with financial penalties are required. | 4-6 weeks | +1.0 points avg
5 | Geofencing + Proof-of-Location | Real estate needs proof the photographer visited the property. Insurance needs proof the inspector was on-site. Logistics needs proof-of-delivery. Without verifiable location, physical task completion is unfalsifiable. | 3-4 weeks | +0.8 points avg
TOTAL: Build these 5 features → every sector jumps from 5.5 avg to 8.0+ avg |  |  | ~28-36 wks parallel → 10-12 wks | +6.3 pts total