## Executive Summary
HumanPages MCP — Road to 9/10
10 Client Archetypes × 10 Gaps = Prioritized Roadmap to Universal 9/10
Archetype | Today | After Plan | Delta | Key Unlock | Tier
Russian crypto user | 6.5 | 9.2 | +2.7 | USDC is survival, not preference | Tier 1
Digital nomad agency | 5 | 9 | +4.0 | Sub-agents + invoicing + projects | Tier 1
Crypto KOL / creator | 4.5 | 9.1 | +4.6 | Recurring templates + file sharing | Tier 2
Crypto trader | 4.3 | 9 | +4.7 | 24/7 shifts + recurring + security | Tier 2
Vibe-coder (Claude) | 4 | 9.3 | +5.3 | Session persistence + escrow + speed | Tier 2
Web3 developer | 4 | 9.1 | +5.1 | Credential verification + milestones | Tier 2
AI SaaS builder | 4 | 9 | +5.0 | SLA + fallback + quality scoring | Tier 2
Telegram bot dev | 3 | 9 | +6.0 | USDT support + bot API + shifts | Tier 2
Mobile app dev | 2.1 | 9 | +6.9 | Fiat on-ramp + file delivery + bulk | Tier 3
Crypto fund analyst | 2.2 | 9 | +6.8 | NDA + multi-sig + team + invoicing | Tier 3
Avg Today: |  | 3.96 | Avg After: |  | 9.07

## Impact Matrix
Gap × Archetype Impact Matrix (0=irrelevant, 1=nice, 2=important, 3=critical)
Gap / Feature | Vibe- coder | Mobile Dev | Crypto Trader | Web3 Dev | Russian Crypto | AI SaaS Builder | Crypto KOL | TG Bot Dev | Nomad Agency | Crypto Fund | Raw Sum | Weighted | Priority Rank
Market Weight | 15% | 8% | 12% | 12% | 10% | 10% | 8% | 6% | 8% | 5%
Escrow + Dispute Resolution | 3 | 2 | 2 | 3 | 1 | 3 | 2 | 2 | 3 | 3 | 24 | 2.28 | 1
Recurring Jobs / Templates | 2 | 2 | 3 | 1 | 3 | 2 | 3 | 2 | 3 | 1 | 22 | 2.09 | 2
File Sharing / Deliverables | 2 | 3 | 1 | 2 | 1 | 2 | 3 | 1 | 2 | 2 | 19 | 1.76 | 3
NDA / Confidentiality | 0 | 1 | 0 | 2 | 0 | 1 | 2 | 0 | 1 | 3 | 10 | 0.81 | 9
Team / Sub-agent Mgmt | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 3 | 2 | 9 | 0.76 | 11
Rate Limit Overhaul | 1 | 2 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 13 | 1.22 | 5
Availability Calendar | 1 | 1 | 2 | 1 | 2 | 1 | 2 | 2 | 1 | 0 | 13 | 1.25 | 4
Credential Verification | 1 | 1 | 0 | 2 | 0 | 1 | 1 | 0 | 1 | 3 | 10 | 0.88 | 6
Session Persistence | 2 | 0 | 0 | 1 | 0 | 2 | 0 | 0 | 0 | 0 | 5 | 0.62 | 12
Invoicing / Tax Docs | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 2 | 2 | 6 | 0.44 | 15
Fiat On-Ramp (card pay) | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 6 | 0.5 | 14
USDT / Multi-token | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 3 | 0.28 | 18
Telegram Bot API Inbound | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 3 | 0.22 | 19
Multi-sig (Safe) Support | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 3 | 5 | 0.35 | 16
Portfolio / Past Work | 1 | 1 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 1 | 6 | 0.56 | 13
Bulk Job Creation | 1 | 2 | 1 | 0 | 0 | 1 | 1 | 0 | 2 | 1 | 9 | 0.82 | 8
Location Verification | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0.16 | 20
SLA / Response Guarantees | 1 | 1 | 2 | 1 | 0 | 2 | 1 | 0 | 0 | 0 | 8 | 0.87 | 7
Quality Scoring System | 1 | 1 | 1 | 1 | 0 | 2 | 1 | 0 | 0 | 1 | 8 | 0.8 | 10
Shift Scheduling | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 3 | 0.32 | 17

## Build Order
Prioritized Build Order — Path to 9/10
# | Feature | Effort | Impact | Executor | What It Unlocks | Ship By | Archetypes Unblocked
1 | Escrow + Dispute Resolution | 2 wk | Critical | Claude + You | Trust for ALL users. #1 gap across every persona. | Week 2 | All 10
2 | Recurring Jobs / Templates | 1 wk | Critical | Claude | Weekly content, daily monitoring, ongoing moderation. | Week 3 | 7 of 10
3 | File Sharing (job attachments) | 1 wk | High | Claude | Send APKs, raw footage, docs. Receive deliverables. | Week 4 | 7 of 10
4 | Rate Limit Overhaul | 3 days | High | Claude | PRO=100/day, org-level limits, no IP cap for auth'd. | Week 4 | 5 of 10
5 | Session Persistence (agent) | 3 days | High | Claude | Agents survive beyond 1hr. Vibe-coder dream works. | Week 5 | 3 of 10
6 | Availability Calendar | 1.5 wk | High | Claude + You | Book time slots. See who's online NOW. Shift planning. | Week 6 | 4 of 10
7 | NDA / Confidentiality Flow | 1 wk | High | Claude | Digital NDA before job access. IP assignment. | Week 7 | 5 of 10
8 | Team / Sub-agent Management | 1.5 wk | High | Claude + You | Org accounts, shared billing, role-based access. | Week 8 | 5 of 10
9 | Credential Verification | 1 wk | Medium | Claude + You | Verify skills via tests, portfolio, LinkedIn. | Week 9 | 4 of 10
10 | Quality Scoring System | 1 wk | Medium | Claude | Auto-score humans by completion rate, speed, reviews. | Week 10 | 4 of 10
11 | SLA / Response Guarantees | 1 wk | Medium | Claude | Guaranteed response in 1h/4h. Auto-escalate if missed. | Week 10 | 3 of 10
12 | Bulk Job Creation | 3 days | Medium | Claude | Create 50 jobs in 1 API call. Batch search+hire. | Week 11 | 4 of 10
13 | Invoicing / Tax Docs | 1 wk | Medium | Claude | Auto-generate invoices, tax summaries, CSV exports. | Week 11 | 3 of 10
14 | Fiat On-Ramp (Coinbase Pay) | 1 wk | Medium | You + Coinbase | Credit card → USDC. Removes crypto barrier. | Week 12 | 2 of 10
15 | Portfolio / Past Work Display | 3 days | Medium | Claude | Show work samples in search results + profiles. | Week 12 | 3 of 10
16 | USDT / Multi-token Support | 3 days | Low | Claude | Accept USDT, DAI. Matters for TG bot devs. | Week 13 | 2 of 10
17 | Shift Scheduling | 1 wk | Low | Claude | 3-shift 24/7 coverage. Timezone-aware rotation. | Week 13 | 2 of 10
18 | Multi-sig (Safe) Support | 1 wk | Low | Claude + You | DAO/fund treasuries can pay directly. | Week 14 | 2 of 10
19 | Telegram Bot API Inbound | 1 wk | Low | Claude | Trigger hiring from your own TG bot. | Week 14 | 2 of 10
20 | Location Verification | 3 days | Low | Claude | Selfie + GPS proof for on-site tasks. | Week 15 | 1 of 10

## Score Trajectory
Score Trajectory — Each Archetype After Each Feature Ships
Archetype | Today | F1 | F2 | F3 | F4 | F5 | F6 | F7 | F8 | F9 | F10 | F11 | F12 | F13 | F14 | F15 | F16 | F17 | F18 | F19 | F20
Feature → |  | Escrow | Recur | Files | Rates | Session | Calendar | NDA | Teams | Creds | Quality | SLA | Bulk | Invoice | Fiat | Portfolio | USDT | Shifts | MultiSig | TG Bot | Location
Vibe-coder (Claude) | 4 | 5.5 | 6.2 | 6.8 | 7.2 | 8 | 8.2 | 8.2 | 8.4 | 8.6 | 8.8 | 9 | 9 | 9 | 9 | 9.1 | 9.1 | 9.1 | 9.1 | 9.2 | 9.3
Mobile app dev | 2.1 | 3.5 | 4 | 5 | 5.5 | 5.8 | 6.2 | 6.5 | 6.5 | 7 | 7.3 | 7.5 | 7.8 | 8 | 8.5 | 8.7 | 8.7 | 8.7 | 8.7 | 8.8 | 9
Crypto trader | 4.3 | 5.5 | 7 | 7.3 | 7.5 | 7.5 | 8.2 | 8.2 | 8.2 | 8.4 | 8.6 | 8.8 | 8.9 | 8.9 | 8.9 | 8.9 | 8.9 | 9 | 9 | 9 | 9
Web3 developer | 4 | 5.5 | 6 | 6.5 | 6.8 | 7 | 7.3 | 7.8 | 7.8 | 8 | 8.5 | 8.7 | 8.7 | 8.8 | 8.8 | 8.9 | 9 | 9 | 9 | 9.1 | 9.1
Russian crypto user | 6.5 | 7.5 | 8 | 8.2 | 8.4 | 8.5 | 8.6 | 8.6 | 8.7 | 8.7 | 8.8 | 8.8 | 8.9 | 9 | 9 | 9 | 9.1 | 9.1 | 9.1 | 9.2 | 9.2
AI SaaS builder | 4 | 5.5 | 6 | 6.5 | 7 | 7.5 | 7.8 | 7.8 | 8 | 8.2 | 8.5 | 8.8 | 8.9 | 8.9 | 8.9 | 9 | 9 | 9 | 9 | 9 | 9
Crypto KOL / creator | 4.5 | 5.5 | 7 | 7.8 | 8 | 8 | 8.3 | 8.3 | 8.3 | 8.5 | 8.7 | 8.7 | 8.8 | 8.8 | 8.9 | 9 | 9 | 9 | 9 | 9.1 | 9.1
Telegram bot dev | 3 | 4 | 5.5 | 5.8 | 6 | 6.2 | 6.5 | 6.5 | 6.5 | 6.8 | 7 | 7 | 7.3 | 7.5 | 7.5 | 7.5 | 8 | 8.5 | 8.5 | 9 | 9
Nomad agency | 5 | 6 | 6.5 | 7 | 7.2 | 7.2 | 7.5 | 7.5 | 8.2 | 8.4 | 8.5 | 8.6 | 8.8 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9
Crypto fund | 2.2 | 3.5 | 3.8 | 4 | 4.2 | 4.2 | 4.5 | 5.5 | 6.5 | 7 | 7.5 | 7.5 | 7.8 | 8.5 | 8.5 | 8.7 | 8.7 | 8.7 | 9 | 9 | 9
AVERAGE | 3.96 | 5.2 | 6 | 6.49 | 6.78 | 6.99 | 7.31 | 7.49 | 7.71 | 7.96 | 8.22 | 8.34 | 8.49 | 8.64 | 8.7 | 8.78 | 8.85 | 8.91 | 8.94 | 9.04 | 9.07
MINIMUM | 2.1 | 3.5 | 3.8 | 4 | 4.2 | 4.2 | 4.5 | 5.5 | 6.5 | 6.8 | 7 | 7 | 7.3 | 7.5 | 7.5 | 7.5 | 8 | 8.5 | 8.5 | 8.8 | 9
MILESTONES
Week 4 (F1-F4) | Avg hits 7.0, worst case hits 4.2. Escrow + recurring + files + rates.
Week 8 (F1-F8) | Avg hits 8.0, worst case hits 6.5. All Critical+High features shipped.
Week 11 (F1-F12) | Avg hits 8.5, worst case hits 7.5. Medium features done.
Week 15 (F1-F20) | Avg hits 9.1, MIN hits 9.0. All archetypes at 9+. DONE.

## Executor Split
Who Builds What — Claude vs You vs Freelancers
Feature | Effort | Executor | Claude Does | You Do
Escrow + Dispute Resolution | 2 wk | Claude + You | Smart contract code, API endpoints, frontend UI, test suite | Deploy contract, fund test escrow, legal review
Recurring Jobs / Templates | 1 wk | Claude | DB schema, API, frontend recurring job UI, cron scheduler | Review + merge PR
File Sharing / Deliverables | 1 wk | Claude | R2 upload/download, API endpoints, frontend dropzone | Review + merge PR
Rate Limit Overhaul | 3 days | Claude | Rewrite rate limiter, org-level tracking, config | Review + merge PR
Session Persistence | 3 days | Claude | JWT refresh, persistent agent sessions, Redis store | Review + merge PR
Availability Calendar | 1.5 wk | Claude + You | Calendar component, booking API, timezone logic | UX review, test with real humans
NDA / Confidentiality | 1 wk | Claude | NDA template, digital signature flow, access control | Legal review of NDA template
Team / Sub-agent Mgmt | 1.5 wk | Claude + You | Org model, role-based access, shared billing | Define roles + permissions matrix
Credential Verification | 1 wk | Claude + You | LinkedIn OAuth verification, skill test framework | Define skill test questions
Quality Scoring System | 1 wk | Claude | Scoring algorithm, completion rate calc, UI badges | Review + merge PR
SLA / Response Guarantees | 1 wk | Claude | SLA tiers, auto-escalation logic, notification retry | Define SLA tiers for market
Bulk Job Creation | 3 days | Claude | Batch API endpoint, bulk search+hire flow | Review + merge PR
Invoicing / Tax Docs | 1 wk | Claude | Invoice PDF generation, tax summary, CSV export | Review + merge PR
Fiat On-Ramp | 1 wk | You + Coinbase | Coinbase Pay integration, frontend widget | Coinbase account setup, API keys
Portfolio / Past Work | 3 days | Claude | Portfolio upload, gallery component, search integration | Review + merge PR
USDT / Multi-token | 3 days | Claude | Token config, Superfluid USDT wrapper, payment router | Review + merge PR
Shift Scheduling | 1 wk | Claude | Shift model, rotation calendar, timezone-aware assignment | Review + merge PR
Multi-sig (Safe) | 1 wk | Claude + You | Safe SDK integration, approval flow, tx batching | Test with real Safe wallet
Telegram Bot API | 1 wk | Claude | Inbound webhook handler, /hire command, TG bot logic | Register bot with BotFather
Location Verification | 3 days | Claude | GPS+selfie upload, metadata validation, geofencing | Review + merge PR
TOTALS
Claude solo: | 11 features
Claude + You: | 7 features
You lead: | 2 features
Your total time: | ~15-20 hours over 15 weeks
Claude total time: | ~200+ hours of code generation

## Per-Archetype Needs
What Each Archetype Needs to Hit 9/10
Archetype | Must-Have Features | Nice-to-Have Features | Score: Today→9+ | Earliest 9/10
Russian crypto user | Escrow, Recurring, File sharing, Rate limits | Invoicing, Portfolio, Multi-token | 6.5 → 9.2 | Week 6
Nomad agency | Escrow, Recurring, Files, Teams, Invoicing | Location verification, Bulk hiring | 5.0 → 9.0 | Week 13
Crypto KOL / creator | Recurring templates, File sharing, Escrow, Portfolio | Calendar, Shift scheduling | 4.5 → 9.1 | Week 12
Crypto trader | Recurring, Calendar, Shift scheduling, Escrow | SLA guarantees, Quality scoring | 4.3 → 9.0 | Week 13
Vibe-coder (Claude) | Escrow, Session persistence, SLA, Quality | Bulk hire, Fiat on-ramp | 4.0 → 9.3 | Week 11
Web3 developer | Credential verification, NDA, Escrow, Files | Multi-sig, Portfolio | 4.0 → 9.1 | Week 12
AI SaaS builder | SLA, Session persistence, Escrow, Quality | Bulk hire, Fiat on-ramp | 4.0 → 9.0 | Week 11
Telegram bot dev | USDT support, TG Bot API, Shifts, Recurring | Escrow, Calendar | 3.0 → 9.0 | Week 14
Mobile app dev | Fiat on-ramp, File sharing, Bulk hire, Escrow | Credential verification, Portfolio | 2.1 → 9.0 | Week 14
Crypto fund analyst | NDA, Multi-sig, Team mgmt, Credential verif, Invoicing | Quality scoring, Portfolio | 2.2 → 9.0 | Week 14